## Tabelle1
Sprint Review Protocol
Sprint No: |  | #3
Date & Time |  | 15.12.2021, 15:30:00
Group Number |  | 29
Participant 1 |  | Stefan Düx
Participant 2 |  | Jessica Isabella Görög
Participant 3 |  | Dominic Grabner
Participant 4 |  | Rebekka Tscheppen
Participant 5 |  | Lukas Varga
Mentor |  | Lukas Rohatsch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | bug - PIL library | 1 | 0.25 | -0.75 | 1
2 | generate data from videos | 3 | 2.5 | -0.5 | 1
3 | test/use new packages | 3 | 2 | -1 | 1
4 | update Jira | 1 | 0.75 | -0.25 | 1
5 | update GitHub | 0.5 | 0.5 | 0 | 1
6 | discuss 3D print | 0.5 | 0.25 | -0.25 | 1
7 | communication ProjectKitchen | 0.5 | 0.5 | 0 | 1
8 | discussion content sprint #5, #6 | 0.5 | 0.25 | -0.25 | 1
8 |  |  |  | -3 | 8 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol