## Tabelle1
Sprint Review Protocol
Sprint No: |  | #10
Date & Time |  | 17.05.2022, 20:50:00
Group Number |  | 29
Participant 1 |  | Stefan Düx
Participant 2 |  | Jessica Isabella Görög
Participant 3 |  | Dominic Grabner
Participant 4 |  | Rebekka Tscheppen
Participant 5 |  | Lukas Varga
Mentor |  | Lukas Rohatsch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | bugfix hardware connecting | 1 | 0.75 | -0.25 | 1
2 | bugfix multithreading | 2 | 5 | 3 |  | 1
3 | bugfix autostart | 2 | 4 | 2 |  | 1
4 | install mqtt | 2 | 0.75 | -1.25 | 1
5 | configure mqtt | 2 | 1 | -1 | 1
6 | fine tuning auto start | 1.5 | 2 | 0.5 | 1
7 | live demo | 1 | 0 | -1 |  | 1
8 | update Jira | 0.5 | 0.5 | 0 | 1
9 | update GitHub | 0.5 | 0.5 | 0 | 1
10 | 3D print | 1.5 | 0 | -1.5 |  | 1
11 | DAGoPERT T-Shirt sizing | 1 | 0.5 | -0.5 | 1
11 |  |  |  | 0 | 7 | 4
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol