## Tabelle1
Sprint Review Protocol
Sprint No: |  | #11
Date & Time |  | 31.05.2022, 19:21:00
Group Number |  | 29
Participant 1 |  | Stefan Düx
Participant 2 |  | Jessica Isabella Görög
Participant 3 |  | Dominic Grabner
Participant 4 |  | Rebekka Tscheppen
Participant 5 |  | Lukas Varga
Mentor |  | Lukas Rohatsch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
#11reqID1_1 | bugfix multithreading on pi | 3 | 1 | -2 |  | 1
#11reqID1_2 | bugfix autostart problem | 3 | 4 | 1 |  | 1
#11reqID2_3 | implement mqtt component on pi | 1 | 1.5 | 0.5 | 1
#11reqID2_4 | fine tuning auto start | 1.5 | 0 | -1.5 |  | 1
#11reqID2_5 | install interface by blueprint | 3.5 | 1 | -2.5 |  | 1
#11reqID2_6 | test interface functionality | 2.5 | 0 | -2.5 |  | 1
#11reqID3_7 | live demo | 2 | 0 | -2 |  | 1
#11reqID4_8 | update Jira | 0.5 | 0.5 | 0 | 1
#11reqID4_9 | update GitHub | 0.5 | 0.5 | 0 | 1
#11reqID4_10 | appointment ProjectKitchen | 2 | 0 | -2 |  | 1
10 |  |  |  | -11 | 3 | 7
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol