## Tabelle1
Sprint Review Protocol
Sprint No: |  | #12
Date & Time |  | 14.06.2022, 19:37:00
Group Number |  | 29
Participant 1 |  | Stefan Düx
Participant 2 |  | Jessica Isabella Görög
Participant 3 |  | Dominic Grabner
Participant 4 |  | Rebekka Tscheppen
Participant 5 |  | Lukas Varga
Mentor |  | Lukas Rohatsch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
#12reqID1_01 | fix multithreading on pi | 2 | 2.5 | 0.5 | 1
#12reqID1_02 | fix autostart problem | 2 | 1.5 | -0.5 | 1
#12reqID1_03 | implement interface | 2 | 0 | -2 |  | 1
#12reqID2_04 | fine tuning auto start | 1 | 0.5 | -0.5 | 1
#12reqID2_05 | test interface functionality | 2 | 0 | -2 |  | 1
#12reqID3_06 | live demo with project group | 2 | 0 | -2 |  | 1
#12reqID4_07 | update Jira tasks | 0.5 | 0.5 | 0 | 1
#12reqID4_08 | update GitHub rep | 0.5 | 0.5 | 0 | 1
#12reqID4_09 | appointment ProjectKitchen | 0.5 | 0.5 | 0 | 1
0 |  |  |  | -6.5 | 6 | 3
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol