## Tabelle1
Sprint Review Protocol
Sprint No: |  | #9
Date & Time |  | 03.05.2022, 21:00:00
Group Number |  | 29
Participant 1 |  | Stefan Düx
Participant 2 |  | Jessica Isabella Görög
Participant 3 |  | Dominic Grabner
Participant 4 |  | Rebekka Tscheppen
Participant 5 |  | Lukas Varga
Mentor |  | Lukas Rohatsch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
#9reqID1_01 | bugfixing | 1 | 0.5 | -0.5 | 1
#9reqID3_02 | implementing software on pi | 1.5 | 1 | -0.5 | 1
#9reqID3_03 | automatic start | 2 | 1.5 | -0.5 | 1
#9reqID3_04 | connect hardware + test | 2 | 1.5 | -0.5 | 1
#9reqID3_05 | test setup live | 2 | 2 | 0 | 1
#9reqID4_06 | jira tasks | 0.5 | 0.5 | 0 | 1
#9reqID4_07 | github rep | 0.5 | 0.5 | 0 | 1
#9reqID4_08 | 3d print appointment | 0.5 | 0.5 | 0 | 1
8 |  |  |  | -2 | 8 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol