## Tabelle1
Sprint Review Protocol
Sprint No: |  | 15
Date & Time |  | 18.10.2022
Group Number |  | 29
Participant 1 |  | Stefan Düx
Participant 2 |  | Jessica Isabella Görög
Participant 3 |  | Dominic Grabner
Participant 4 |  | Rebekka Tscheppen
Participant 5 |  | Lukas Varga
Mentor |  | Lukas Rohatsch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
TO29-316 | Browse for new/more adequat solution | 6 | 2 | -4
TO29-317 | Implementation on Windows system | 6 | 1.5 | -4.5
TO29-311 | Testing of performance and functionality on Windows system | 4 | 1 | -3
TO29-342 | clean / refactor repository | 2 | 1 | -1
TO29-386 | research different frameworks | 2 | 0 | -2
TO29-377 | Choose Framework | 2 | 0 | -2
TO29-387 | setup framework | 4 | 0 | -4
TO29-325 | Request 3D print at ProjectKitchen (made appointment) | 2 | 0.5 | -1.5
TO29-326 | Send data to print | 2 | 0.5 | -1.5
TO29-327 | Wait for print | 2 | 2 | 0
TO29-328 | Pickup printed 3D case | 2 | 0.5 | -1.5
11 |  |  |  | -25 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol