## Tabelle1
Sprint Review Protocol
Sprint No: |  | #8
Date & Time |  | 19.04.2022, 19:00:00
Group Number |  | 29
Participant 1 |  | Stefan Düx
Participant 2 |  | Jessica Isabella Görög
Participant 3 |  | Dominic Grabner
Participant 4 |  | Rebekka Tscheppen
Participant 5 |  | Lukas Varga
Mentor |  | Lukas Rohatsch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
#8reqID1_01 | bugfix | 5 | 4 | -1 | x
#8reqID2_02 | decision for final version | 1 | 1 | 0 | x
#8reqID2_03 | interface discussion | 0.5 | 0.5 | 0 | x
#8reqID3_04 | implement software on pi | 3 |  | -3 |  | x
#8reqID3_05 | test automatic start | 2 |  | -2 |  | x
#8reqID3_06 | connect hardware | 1.5 |  | -1.5 |  | x
#8reqID3_06_2 | try NoIR module | 2 |  | -2 |  | x
#8reqID3_06_3 | browse for alternative cameras | 2 | 1.5 | -0.5 | x
#8reqID4_07 | update Jira tasks | 0.5 | 0.5 | 0 | x
#8reqID4_08 | update GitHub rep | 0.5 | 0.5 | 0 | x
#8reqID4_09 | contact ProjektKitchen | 0.5 | 0.5 | 0 |  | x
#8reqID4_10 | redo time effort estimation | 1.5 | 2 | 0.5 | x
#8reqID4_11 | add Tshirt sizing | 1 |  | -1 |  | x
#8reqID4_12 | choose mockup for interface | 0.5 | 0.5 | 0 | x
#8reqID4_13 | finalize mockup | 1 | 0.75 | -0.25 | x
#8reqID4_14 | change appointment supervisor | 0.5 | 0.5 | 0 | x
16 |  |  |  | -10.75 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol