## Tabelle1
Sprint Review Protocol
Sprint No: |  | 16
Date & Time |  | 08.11.2022
Group Number |  | 29
Participant 1 |  | Stefan Düx
Participant 2 |  | Jessica Isabella Görög
Participant 3 |  | Dominic Grabner
Participant 4 |  | Rebekka Tscheppen
Participant 5 |  | Lukas Varga
Mentor |  | Lukas Rohatsch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
TO29-348 | create new branch | 2 | 0.5 | -1.5
TO29-316 | Browse for new/more adequat solutions | 10 | 6 | -4
TO29-317 | Implementation on Windows system | 4 | 2 | -2
TO29-318 | Testing performance/functionality on Windows system | 4 | 0 | -4
TO29-331 | Install flask (sending camera stream to webpage) | 4 | 1.5 | -2.5
TO29-319 | Reset Raspberry Pi | 2 | 1.5 | -0.5
TO29-320 | Install all necessary packages / DB | 6 | 2 | -4
TO29-321 | Install source code synch application | 4 | 1 | -3
TO29-322 | Prepare directory for project + synch current code | 2 | 1 | -1
TO29-386 | research different frameworks | 2 | 1 | -1
TO29-377 | Choose Framework | 2 | 0.5 | -1.5
TO29-387 | setup framework | 4 | 1.5 | -2.5
TO29-378 | design interface | 2 | 0.75 | -1.25
TO29-388 | make interface mockup | 2 | 1 | -1
TO29-379 | implement skeleton | 4 | 2 | -2
TO29-328 | Pickup printed 3D case | 1 | 0.5 | -0.5
TO29-332 | Request for database access (Grafana + InfluxDB) | 2 | 0 | -2
TO29-333 | Setup datatable columns | 6 | 0 | -6
16 |  |  |  | -40.25 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol