## time_Stefan
| Stefan Düx |  |  |  |  | current hours of work - group in total: |  | 145:13
semester #3: | 30:23 | semester #5: |  | 30:40 | developer 0 |  | (group) semester #3: | 169:13
semester #4: | 61:55 | [5 empty] | (group) semester #4: | 221:56
# | date | start | end | duration | content of work
1 | 2021-09-23 | 16:00 | 17:45 | 1:45 | Class 1: Course Startup (discuss project topics to choose, plan to form group together)
2 | 2021-09-23 | 19:00 | 19:50 | 0:50 | chose topic 29 (visitor counter) and formed group via project selection tool
3 | 2021-10-06 | 17:00 | 18:00 | 1:00 | discussed and documentated first ideas of requirements, ORDER questions and collaborations tools
4 | 2021-10-07 | 8:00 | 9:00 | 1:00 | Class 2: presented project supervisor requirements and collaboration tools; got information for project / routines; made appointment for picking up hardware
5 | 2021-10-10 | 19:45 | 20:00 | 0:15 | group meeting ( format of timetable / kanban board / documentation discussed)
6 | 2021-10-11 | 14:20 | 16:00 | 1:40 | group meeting (prepare documentation for self study C)
7 | 2021-10-12 | 16:10 | 16:45 | 0:35 | class 3 - presentation of project diary (chapter 1+2), effort estimation, requirement priorities and sprint planning
8 | 2021-10-14 | 10:30 | 10:45 | 0:15 | Presentation Lab visit (taking measures, photos, brainstorming for positioning of pi+cam)
9 | 2021-11-03 | 9:40 | 11:00 | 1:20 | Team meeting (hardware requirements sprint 1 - reqID3_#1, reqID3_#2)
10 | 2021-11-10 | 17:15 | 18:20 | 1:05 | Research which OS to use for the Rasperry Pi. Choose IDE for Python and installed.
11 | 2021-11-11 | 16:10 | 16:45 | 0:35 | class 4 - presentation of sprint#1, requirements sprint#2, documentation, PoE malfunction
12 | 2021-11-24 | 19:00 | 20:10 | 1:10 | sprint meeting (sprint #2 final)
13 | 2021-11-25 | 16:10 | 16:45 | 0:35 | class 5 - presentation of sprint#2; requirements sprint#3; Jira; 3D print next steps; PoE status
14 | 2021-11-25 | 10:00 | 14:30 | 4:30 | Installed opencv on personal pc, set up python virtual environment in pycharm and started testing basic functionality of the program.
15 | 2021-11-26 | 11:30 | 12:00 | 0:30 | weekly sprint meeting - discuss assigned tasks; connected GitHub Repository; arranged date for tutorial
16 | 2021-11-27 | 14:00 | 15:30 | 1:30 | opencv basic setup and use tutorium
17 | 2021-12-08 | 19:00 | 19:24 | 0:24 | team meeting(sprint #3 final)
18 | 2021-12-09 | 16:10 | 16:30 | 0:20 | meeting with lecturer for to close out sprint #3
19 | 2021-12-15 | 15:05 | 16:07 | 1:02 | team meeting (sprint #4 final)
20 | 2021-12-16 | 16:10 | 16:45 | 0:35 | class 7 - presentation of sprint #4; requirements sprint #5; Jira
21 | 2021-12-30 | 17:55 | 19:57 | 2:02 | looking up tutorials for templates and fixes for delivery speed issues
22 | 2022-01-12 | 18:30 | 19:15 | 0:45 | team meeting (sprint #5 final)
23 | 2022-01-13 | 15:15 | 16:00 | 0:45 | class 8 - presentation of sprint #5; requirements sprint #6; Jira
24 | 2022-01-15 | 12:10 | 14:05 | 1:55 | tried out multithreaded python examples and fixed issue with imutils package not loading in pycharm
25 | 2022-01-16 | 10:00 | 13:15 | 3:15 | preparing the script and capturing the video for the last spring with obs
26 | 2022-01-20 | 15:15 | 16:00 | 0:45 | class 9 - feedback of final upload; discussion about upcoming semester phase; sharing information to mqtt etc
1 | 2022-03-15 | 19:45 | 21:10 | 1:25 | created effort estimation using DAGoPERT template; specified requirements sprint #7; uploaded required documents; updated repository; group meeting
2 | 2022-03-18 | 12:50 | 13:35 | 0:45 | class 2 - meeting to discuss preparations, plan and tasks up to now for sprint #7/#1_2
3 | 2022-03-25 | 10:00 | 16:00 | 6:00 | Researched about alternate methods of object detection using threshholding and color-substraction
4 | 2022-03-27 | 17:15 | 21:10 | 3:55 | Implemented demo for alternate method using opencv and sample pictures
5 | 2022-03-28 | 18:10 | 21:45 | 3:35 | Tried to implement code, which uses thresholding to detect moving objects on greyscale images substracted fomr life footage, to work with our sample footage
6 | 2022-03-29 | 20:00 | 21:00 | 1:00 | team meeting (sprint #7) to upload sprint review protocol #7 & create requirements sprint #8
7 | 2022-03-31 | 16:30 | 17:00 | 0:30 | team meeting (sprint #7) to discuss last changes and prepare for meeting with supervisor
8 | 2022-04-10 | 17:30 | 22:20 | 4:50 | Tried to optimize code to work with our sample footage using the alternate detection method
9 | 2022-04-17 | 11:10 | 14:30 | 3:20 | Researched the impact of different camera modules (e.g. infrared) for object detection as well as which modules are available for the pi with the team
10 | 2022-04-19 | 18:30 | 19:30 | 1:00 | team meeting; upload sprint review protocol; specifiying requirements sprint #08
11 | 2022-04-21 | 13:00 | 13:45 | 0:45 | class 4 - presentation of sprint #08, requirements sprint #09
12 | 2022-05-01 | 19:00 | 20:00 | 1:00 | Research about parallelising image processing when using opencv on pi
13 | 2022-05-02 | 16:00 | 18:10 | 2:10 | team meeting; connecting hardware (pi, camera with new software)
14 | 2022-05-03 | 19:30 | 21:30 | 2:00 | team meeting; upload sprint review protocol; specifiying requirements sprint #09
15 | 2022-05-05 | 16:00 | 16:45 | 0:45 | class 5 - presentation of sprint #09, requirements sprint #10
16 | 2022-05-17 | 19:00 | 21:05 | 2:05 | team meeting; upload sprint review protocol; specifiying requirements sprint #10
17 | 2022-05-20 | 12:30 | 13:15 | 0:45 | class 6 - presentation of sprint #10, requirements sprint #11
18 | 2022-05-25 | 20:00 | 22:00 | 2:00 | Researched about multithreading on python and the limitations introduced by the GIL(Global Interpreter Lock) which prevents true multihreading for CPU heavy tasks
19 | 2022-05-28 | 8:00 | 13:00 | 5:00 | Implemented demo code using multiprocessing to cirumvent the GIL issue and enhance performance of software by parallelizing tasks
20 | 2022-05-31 | 18:00 | 20:20 | 2:20 | team meeting; upload sprint review protocol; specifiying requirements sprint #11
21 | 2022-06-01 | 19:00 | 19:45 | 0:45 | class 7 - presentation of sprint #11, requirements sprint #12
22 | 2022-06-11 | 10:00 | 16:00 | 6:00 | Researched more about how to correctly use multiprocessing on rasperry pi and which factors enhance the opencv library performance as well as trying to implement the correct code
23 | 2022-06-14 | 17:50 | 19:55 | 2:05 | team meeting; upload sprint review protocol; specifiying requirements sprint #12
24 | 2022-06-15 | 16:00 | 16:45 | 0:45 | class 8 - presentation of sprint #12, requirements sprint #13
25 | 2022-06-18 | 11:00 | 16:20 | 5:20 | Unsuccessfully tried to enhance the perfromance of the program on when running on pi, monitoring cpu cores to try and find out which changes showed best results
26 | 2022-06-21 | 10:40 | 12:30 | 1:50 | Created video content covering the approaches used for person detecting (Multiprocessing and Class based threading) as well as the issues when dealing with lacking performance for cpu heavy operations on the pi
1 | 2022-09-23 | 20:00 | 20:30 | 0:30 | pre-sprint meeting start of semester
2 | 2022-09-30 | 19:00 | 19:15 | 0:15 | New backlog items
3 | 2022-09-30 | 19:45 | 20:45 | 1:00 | pre-sprint meeting #2
4 | 2023-10-03 | 18:30 | 19:30 | 1:00 | task and discussion dagopert effort estimation
5 | 2022-10-06 | 16:10 | 16:40 | 0:30 | sprint #15 lecturer meeting
6 | 2022-10-27 | 13:30 | 17:30 | 4:00 | choose framework, setup angular base, created updated mockups
7 | 2022-11-08 | 13:00 | 16:00 | 3:00 | added ionic module to project and created skeleton
8 | 2022-11-09 | 16:15 | 17:00 | 0:45 | added some formatting to website, as well as dummy data
9 | 2022-11-09 | 18:20 | 18:35 | 0:15 | sprint #16 lecturer meeting
10 | 2022-11-22 | 14:00 | 17:15 | 3:15 | trying to get the pdm to work in order to make displaying the live feed possible, not working yet
11 | 2022-11-23 | 18:00 | 18:45 | 0:45 | sprint #17 lecturer meeting
12 | 2022-12-06 | 15:00 | 18:30 | 3:30 | researching mqtt for angular, trying to adapt to project
13 | 2022-12-20 | 14:50 | 17:00 | 2:10 | mqtt not working with angular, tryout of different standalone examples with open source brokers
14 | 2023-01-14 | 13:00 | 14:00 | 1:00 | group meeting to discuss overall progress and tasks
15 | 2023-01-14 | 14:00 | 17:30 | 3:30 | found cause of mqtt-error with timeout, because websockets need to be configured on the fh-brocker
16 | 2023-01-23 | 17:30 | 18:15 | 0:45 | sprint #18 lecturer meeting
17 | 2023-01-29 | 13:00 | 17:30 | 4:30 | Final preparation fnishing project paper and providing material for advertisement-video
How to use:
for a new entry of time & work start a new line with typing in the proper date and time your started your work
the number of entry (column ‘C’) will appear after starting time is confirmed
type in your ending time in column ‘F’ and after confirming it, your time of work will be calculated and added to the sum
recording what you did with that time, put your work of content in the same line at column ‘H’
“ctrl” + “ü” adds the current date
Thanks for participating!

## time_Lukas
| Lukas Varga |  |  |  |  | current hours of work - group in total: |  | 145:13
semester #3: | 44:43 | semester #5: |  | 31:14 | developer 4 |  | (group) semester #3: | 169:13
semester #4: | 50:02 | [5 empty] | (group) semester #4: | 221:56
# | date | start | end | duration | content of work
1 | 2021-09-23 | 16:00 | 17:45 | 1:45 | Class 1: Course Startup (discuss project topics to choose, plan to form group together)
2 | 2021-09-23 | 19:00 | 19:50 | 0:50 | chose topic 29 (visitor counter) and formed group via project selection tool
3 | 2021-10-06 | 17:00 | 18:00 | 1:00 | discussed and documentated first ideas of requirements, ORDER questions and collaborations tools
4 | 2021-10-07 | 8:00 | 9:00 | 1:00 | Class 2: presented project supervisor requirements and collaboration tools; got information for project / routines; made appointment for picking up hardware
5 | 2021-10-08 | 19:00 | 21:20 | 2:20 | creating trello board + project schedule (basic data, collaboration tools, member list, management-summary, frame conditions)
6 | 2021-10-10 | 19:45 | 20:00 | 0:15 | group meeting ( format of timetable / kanban board / documentation discussed)
7 | 2021-10-11 | 14:20 | 16:00 | 1:40 | group meeting (prepare documentation for self study C)
8 | 2021-10-11 | 20:00 | 21:50 | 1:50 | formatted current documentation; translated to english; used the most stupid software ever (office 365 online); prepared and uploaded documentation for class 3
9 | 2021-10-12 | 16:10 | 16:45 | 0:35 | class 3 - presentation of project diary (chapter 1+2), effort estimation, requirement priorities and sprint planning
10 | 2021-10-14 | 10:30 | 10:45 | 0:15 | Presentation Lab visit (taking measures, photos, brainstorming for positioning of pi+cam)
11 | 2021-11-03 | 9:40 | 11:00 | 1:20 | Team meeting (hardware requirements sprint 1 - reqID3_#1, reqID3_#2)
12 | 2021-11-09 | 19:30 | 21:20 | 1:50 | create 3D model of Presentation Lab for orientation while planning project, added photos and video from Presentation Lab to Notes
13 | 2021-11-10 | 10:10 | 10:40 | 0:30 | preperation of sprint #2
14 | 2021-11-10 | 19:00 | 20:00 | 1:00 | team meeting (sprint #1 final)
15 | 2021-11-10 | 20:00 | 20:15 | 0:15 | adapted trello tasks (format) and prepared checklist for meeting with supervisor
16 | 2021-11-11 | 16:10 | 16:45 | 0:35 | class 4 - presentation of sprint#1, requirements sprint#2, documentation, PoE malfunction
17 | 2021-11-12 | 11:30 | 12:00 | 0:30 | weekly sprint meeting (assign tasks)
18 | 2021-11-21 | 13:00 | 16:11 | 3:11 | browsed for 3D model blueprints; wrote email to ProjectKitchen & htw office; planed, discussed and switched to Jira Software + Confluence for advanced documentation
19 | 2021-11-23 | 20:13 | 21:01 | 0:48 | adapted tasks; created process types and assigned pictures for better recognition; changed labels
20 | 2021-11-24 | 11:55 | 12:53 | 0:58 | prepared sprint review protocol #2; added jira task for upcoming meeting; added confluence page for sprint #3 requirements
21 | 2021-11-24 | 18:40 | 19:00 | 0:20 | wrote down information from email for 3D print; discussed next step with Dominic
22 | 2021-11-24 | 19:00 | 20:10 | 1:10 | team meeting (sprint #2 final)
23 | 2021-11-24 | 20:10 | 20:30 | 0:20 | explained Jira to Rebekka for upcoming tasks and general handling
24 | 2021-11-25 | 11:10 | 11:41 | 0:31 | assigned Admin rights to Dominic and Rebekka for Jira; added requirement for Sprint#3; discussed Jira settings
25 | 2021-11-25 | 16:10 | 16:45 | 0:35 | class 5 - presentation of sprint#2; requirements sprint#3; Jira; 3D print next steps; PoE status
26 | 2021-11-26 | 6:00 | 6:12 | 0:12 | closing Trello Board; deleting Google Document; customize timetable; set up task for weekly sprint meeting
27 | 2021-11-26 | 11:30 | 12:00 | 0:30 | weekly sprint meeting - discuss assigned tasks; connected GitHub Repository; arranged date for tutorial
28 | 2021-11-26 | 12:13 | 12:34 | 0:21 | answer email contact for ProjectKitchen
29 | 2021-11-27 | 14:00 | 14:45 | 0:45 | tutorium for opencv
30 | 2021-11-28 | 18:35 | 18:46 | 0:11 | edited jira tasks
31 | 2021-12-08 | 14:00 | 15:04 | 1:04 | call with matthias from projectkitchen; adapt tasks; think of next steps for 3D print; preparation sprint meeting (review protocol, tasks, requirements)
32 | 2021-12-08 | 19:00 | 19:24 | 0:24 | team meeting (sprint #3 final)
33 | 2021-12-09 | 16:10 | 16:45 | 0:35 | class 6 - presentation of sprint #3; requirements sprint #4; Jira; ongoing sprints until end of semester #3
34 | 2021-12-10 | 12:00 | 12:30 | 0:30 | weekly sprint meeting - discussed and assigned tasks; planned timing for next meeting (real life meeting); discussed plan for final 2 sprints
35 | 2021-12-10 | 14:30 | 15:00 | 0:30 | answered ProjectKitchen regarding delay of 3D print; saved screenshot of mail; set up regarding task in Jira
36 | 2021-12-15 | 5:35 | 6:00 | 0:25 | adapt settings; prepare for meeting
37 | 2021-12-15 | 6:45 | 7:58 | 1:13 | capture video via opencv
38 | 2021-12-15 | 9:46 | 11:31 | 1:45 | tried version of people recognizing program
39 | 2021-12-15 | 15:05 | 16:07 | 1:02 | team meeting (sprint #4 final)
40 | 2021-12-16 | 16:10 | 16:45 | 0:35 | class 7 - presentation of sprint #4; requirements sprint #5; Jira
41 | 2022-01-12 | 13:19 | 14:58 | 1:39 | adapted code with multithreading
42 | 2022-01-12 | 18:30 | 19:15 | 0:45 | team meeting (sprint #5 final)
43 | 2022-01-13 | 6:00 | 7:42 | 1:42 | bugfix (operation on Windows); bugfix (text output); ~bugfix (speed); updated repository
44 | 2022-01-13 | 15:15 | 16:00 | 0:45 | class 8 - presentation of sprint #5; requirements sprint #6; Jira
45 | 2022-01-15 | 16:20 | 18:19 | 1:59 | answering mail to ProjectKitchen; summarize/prepare documentation for final upload semester #3; tried to synch python project but confronted some bugs
46 | 2022-01-16 | 14:20 | 14:50 | 0:30 | post-editing of project diary
47 | 2022-01-16 | 15:30 | 16:32 | 1:02 | create powerpoint as part of formal requirements for final class semester #3
48 | 2022-01-18 | 8:55 | 9:06 | 0:11 | research grading requirements; email to supervisor to clarify upload of timetable
49 | 2022-01-20 | 15:15 | 16:00 | 0:45 | class 9 - feedback of final upload; discussion about upcoming semester phase; sharing information to mqtt etc
1 | 2022-01-20 | 18:32 | 18:55 | 0:23 | prepare timetable for upcoming semester
2 | 2022-02-28 | 6:54 | 7:03 | 0:09 | prepare reminders for fixed upload deadlines of documents independent from actual meeting with supervisor
3 | 2022-03-15 | 19:45 | 21:11 | 1:26 | created effort estimation using DAGoPERT template; specified requirements sprint #7; uploaded required documents; updated repository; group meeting
4 | 2022-03-18 | 6:00 | 6:34 | 0:34 | communication supervisor to arrange meeting; updated Jira tasks and assigned to each team member
5 | 2022-03-18 | 12:50 | 13:35 | 0:45 | class 2 - meeting to discuss preparations, plan and tasks up to now for sprint #7/#1_2
6 | 2022-03-19 | 5:45 | 7:00 | 1:15 | updated Jira Tasks + Backlog elements; wrote email to ProjectKitchen for appointment of 3D printing
7 | 2022-03-25 | 10:19 | 11:20 | 1:01 | research for people detection in different scope; wrote down links to sources in notes (25.03.2022)
8 | 2022-03-28 | 16:00 | 17:00 | 1:00 | research; meeting
9 | 2022-03-29 | 20:00 | 21:00 | 1:00 | team meeting (sprint #7) to upload sprint review protocol #7 & create requirements sprint #8
10 | 2022-03-31 | 16:30 | 17:00 | 0:30 | team meeting (sprint #7) to discuss last changes and prepare for meeting with supervisor
11 | 2022-04-14 | 16:34 | 16:49 | 0:15 | request supervisor for new appointment
12 | 2022-04-16 | 15:11 | 16:47 | 1:36 | discussion interface; decision final software
13 | 2022-04-17 | 11:00 | 14:41 | 3:41 | team meeting; added DAGoBERT effort estimation; browse camera module alternatives
14 | 2022-04-19 | 18:30 | 19:30 | 1:00 | team meeting; upload sprint review protocol; specifiying requirements sprint #08
15 | 2022-04-19 | 19:35 | 20:20 | 0:45 | update GitHub, Jira
16 | 2022-04-21 | 13:00 | 13:45 | 0:45 | class 4 - presentation of sprint #08, requirements sprint #09
17 | 2022-04-30 | 6:08 | 8:22 | 2:14 | research autostart python scripts on linux
18 | 2022-04-30 | 9:00 | 10:44 | 1:44 | try to implement autostart
19 | 2022-04-30 | 17:31 | 18:05 | 0:34 | writing email regarding 3d print
20 | 2022-05-02 | 16:00 | 18:09 | 2:09 | team meeting; connecting hardware (pi, camera with new software)
21 | 2022-05-03 | 19:30 | 21:30 | 2:00 | team meeting; upload sprint review protocol; specifiying requirements sprint #09
22 | 2022-05-05 | 16:00 | 16:45 | 0:45 | class 5 - presentation of sprint #09, requirements sprint #10
23 | 2022-05-15 | 18:30 | 19:52 | 1:22 | bugfix hardware connection; DAGoBERT T-Shirt sizing
24 | 2022-05-17 | 19:00 | 21:05 | 2:05 | team meeting; upload sprint review protocol; specifiying requirements sprint #10
25 | 2022-05-20 | 12:30 | 13:15 | 0:45 | class 6 - presentation of sprint #10, requirements sprint #11
26 | 2022-05-31 | 12:50 | 14:30 | 1:40 | implementing mqtt on raspberry pi
27 | 2022-05-31 | 18:00 | 20:17 | 2:17 | team meeting; upload sprint review protocol; specifiying requirements sprint #11
28 | 2022-06-01 | 19:00 | 19:45 | 0:45 | class 7 - presentation of sprint #11, requirements sprint #12
29 | 2022-06-11 | 7:10 | 9:17 | 2:07 | fixed autostart problem
30 | 2022-06-14 | 17:50 | 19:55 | 2:05 | team meeting; upload sprint review protocol; specifiying requirements sprint #12
31 | 2022-06-15 | 16:00 | 16:45 | 0:45 | class 8 - presentation of sprint #12, requirements sprint #13
32 | 2022-06-16 | 11:30 | 12:25 | 0:55 | phone call with ProjectKitchen
33 | 2022-06-20 | 18:40 | 19:04 | 0:24 | contact with ProjectKitchen (we will get permissions and introduction in summer or beginning of upcoming semester)
34 | 2022-06-21 | 14:30 | 16:00 | 1:30 | guest talk
35 | 2022-06-21 | 16:11 | 18:00 | 1:49 | created video content for final video
36 | 2022-06-23 | 10:00 | 13:26 | 3:26 | cut / edited video for upload
37 | 2022-06-26 | 6:50 | 8:55 | 2:05 | adding missing data to documents
38 | 2022-06-26 | 11:29 | 12:00 | 0:31 | upload of final content
1 | 2022-07-03 | 8:45 | 9:10 | 0:25 | preparing documents for last semester usage
2 | 2022-09-14 | 20:45 | 20:55 | 0:10 | Email Supervisor (request for first meeting)
3 | 2022-09-23 | 18:00 | 19:50 | 1:50 | preparing administration (jira, documents, GitHub status, upcoming meeting) and tasks
4 | 2022-09-23 | 20:00 | 20:30 | 0:30 | team meeting; discuss topics and tasks for first upload
5 | 2022-09-30 | 10:30 | 12:30 | 2:00 | backlog definitions
6 | 2022-09-30 | 13:25 | 14:00 | 0:35 | prepare DAGoPERT effort estimation; update backlog
7 | 2022-09-30 | 18:30 | 19:50 | 1:20 | update backlog; prepare DAGoPERT effort estimation
8 | 2022-09-30 | 20:00 | 20:40 | 0:40 | team meeting; discuss backlog + effort estimation
9 | 2022-10-03 | 18:00 | 20:00 | 2:00 | start sprint #15; browse alternative person-recognition software
10 | 2022-10-04 | 20:17 | 21:35 | 1:18 | adapt / assign epics to backlog items; add backlog items & effort estimation to project diary; upload updated project diary
11 | 2022-10-05 | 20:50 | 21:08 | 0:18 | set up sprint task protocol
12 | 2022-10-18 | 14:30 | 15:00 | 0:30 | pickup 3D printed case of raspberry pi
13 | 2022-10-22 | 9:00 | 10:00 | 1:00 | planning time & tasks; start sprint#16 on jira; communication with group; story point entries on jira subtasks
14 | 2022-10-23 | 16:25 | 18:20 | 1:55 | discussions: 3d case styling, branch work, frame skipping (using single frames instead complete video stream), reseting pi and installing server-image
15 | 2022-10-24 | 17:00 | 17:20 | 0:20 | team meeting; discuss amount of sprint tasks to fulfill; possible date/time for meeting with supervisor; discuss current status
16 | 2022-11-08 | 23:00 | 23:54 | 0:54 | sprint review protocol; update jira; prepare raspberry pi
17 | 2022-11-09 | 18:20 | 18:45 | 0:25 | class 4 - presentation sprint #16
18 | 2022-11-23 | 12:00 | 13:00 | 1:00 | prepare sprint review + next sprint
19 | 2022-11-23 | 18:00 | 18:45 | 0:45 | class 5 - presentation sprint #17
20 | 2022-12-07 | 17:30 | 18:30 | 1:00 | influxdb setup / connection - listening for input
21 | 2022-12-07 | 13:00 | 13:45 | 0:45 | administration (sprint review protocol #18, sprint planning #19)
22 | 2022-12-07 | 14:30 | 15:15 | 0:45 | class 6 - presentation sprint #18
23 | 2022-12-13 | 16:15 | 16:50 | 0:35 | meeting supervisor questions influxDB
24 | 2022-12-21 | 17:00 | 17:45 | 0:45 | class 7 - presentation sprint #19
25 | 2023-01-01 | 16:00 | 18:00 | 2:00 | hardware setup (os lite; autostart; source code sync)
26 | 2023-01-12 | 19:35 | 20:15 | 0:40 | colorize 3D case
27 | 2023-01-21 | 4:22 | 6:12 | 1:50 | hardware dependencie install
28 | 2023-01-23 | 17:30 | 18:00 | 0:30 | class 8 - presentation sprint #20
29 | 2023-01-31 | 19:30 | 23:59 | 4:29 | paper, timetable, upload
How to use:
for a new entry of time & work start a new line with typing in the proper date and time your started your work
the number of entry (column ‘C’) will appear after starting time is confirmed
type in your ending time in column ‘F’ and after confirming it, your time of work will be calculated and added to the sum
recording what you did with that time, put your work of content in the same line at column ‘H’
“ctrl” + “ü” adds the current date
Thanks for participating!

## time_Rebekka
| Rebekka Tscheppen |  |  |  |  | current hours of work - group in total: |  | 145:13
semester #3: | 30:17 | semester #5: |  | 28:55 | developer 3 |  | (group) semester #3: | 169:13
semester #4: | 34:16 | [5 empty] | (group) semester #4: | 221:56
# | date | start | end | duration | content of work
1 | 2021-09-23 | 16:00 | 17:45 | 1:45 | Class 1: Course Startup (discuss project topics to choose, plan to form group together)
2 | 2021-09-23 | 19:00 | 19:50 | 0:50 | chose topic 29 (visitor counter) and formed group via project selection tool
3 | 2021-10-06 | 17:00 | 18:00 | 1:00 | discussed and documentated first ideas of requirements, ORDER questions and collaborations tools
4 | 2021-10-07 | 8:00 | 9:00 | 1:00 | Class 2: presented project supervisor requirements and collaboration tools; got information for project / routines; made appointment for picking up hardware
5 | 2021-10-10 | 19:45 | 20:00 | 0:15 | group meeting ( format of timetable / kanban board / documentation discussed)
6 | 2021-10-11 | 14:20 | 16:00 | 1:40 | group meeting (prepare documentation for self study C)
7 | 2021-10-12 | 16:10 | 16:45 | 0:35 | Class 3 - presentation of project diary (chapter 1+2), effort estimation, requirement priorities and sprint planning
8 | 2021-10-14 | 10:30 | 10:45 | 0:15 | Presentation Lab visit (taking measures, photos, brainstorming for positioning of pi+cam)
9 | 2021-11-03 | 9:40 | 11:00 | 1:20 | Team meeting (hardware requirements sprint 1 - reqID3_#1, reqID3_#2)
10 | 2021-11-10 | 17:15 | 18:20 | 1:05 | OS alternatives research + IDE setup (PyCharm)
11 | 2021-11-10 | 18:30 | 19:00 | 0:30 | IDE + Python testing
12 | 2021-11-10 | 19:00 | 20:00 | 1:00 | Team meeting end of sprint1 and sprint 2 planning
13 | 2021-11-11 | 16:10 | 16:45 | 0:35 | class 4 - presentation of sprint#1, requirements sprint#2, documentation, PoE malfunction
14 | 2021-11-12 | 11:30 | 12:00 | 0:30 | team meeting, sprint 2 planning
15 | 2021-11-12 | 12:10 | 12:30 | 0:20 | trello tutorial
16 | 2021-11-12 | 17:45 | 18:00 | 0:15 | sprint2 #12 - create milestones, sprint2 #6 update trello tasks
17 | 2021-11-24 | 14:20 | 14:30 | 0:10 | create Git repository
18 | 2021-11-24 | 19:00 | 20:10 | 1:10 | sprint2 end meeting, sprint 3 planning
19 | 2021-11-24 | 20:10 | 20:30 | 0:20 | jira tutorial
20 | 2021-11-25 | 11:10 | 12:10 | 1:00 | TO29-69 linked github on jira, TO29-68 update jira tasks, try out jira
21 | 2021-11-25 | 16:10 | 16:45 | 0:35 | class 5 - presentation of sprint#2; requirements sprint#3; Jira; 3D print next steps; PoE status
22 | 2021-11-26 | 11:20 | 11:30 | 0:10 | jira sprint 2 complete, spritn 3 start, created issue
23 | 2021-11-26 | 11:30 | 12:02 | 0:32 | sprint 3 meeting
24 | 2021-11-27 | 14:00 | 14:43 | 0:43 | meeting, install opencv, test opencv
25 | 2021-12-08 | 19:00 | 19:25 | 0:25 | sprint 3 end meeting
26 | 2021-12-09 | 16:10 | 16:30 | 0:20 | class 6 - presentation of sprint#3, requiremnts sprint#3
27 | 2021-12-10 | 12:00 | 12:30 | 0:30 | team meeting
28 | 2021-12-10 | 14:30 | 15:00 | 0:30 | communicate with project kitchen
29 | 2021-12-10 | 15:00 | 15:15 | 0:15 | update jira task, confluence notes, pull GitHub repository
30 | 2021-12-15 | 15:05 | 16:07 | 1:02 | team meeting (sprint #4 final)
31 | 2021-12-16 | 16:10 | 16:45 | 0:35 | class 7 - presentation of sprint #4; requirements sprint #5; Jira
32 | 2021-12-18 | 15:31 | 15:50 | 0:19 | update jira tasks
33 | 2021-12-27 | 16:15 | 18:37 | 2:22 | research python bug fixes for more accurate people recognition
34 | 2022-01-01 | 13:55 | 14:42 | 0:47 | update github, setting up ide, test program
35 | 2022-01-12 | 18:30 | 19:15 | 0:45 | team meeting (sprint #5 final)
36 | 2022-01-13 | 15:15 | 16:00 | 0:45 | class 8 - presentation of sprint #5; requirements sprint #6; Jira
37 | 2022-01-15 | 14:00 | 14:19 | 0:19 | update jira tasks, research jira problem with assigning tasks to people
38 | 2022-01-15 | 16:20 | 18:18 | 1:58 | ProjectKitchen email, final documentation, git fetching bug
39 | 2022-01-16 | 12:25 | 14:15 | 1:50 | documentation formatting
1 | 2022-03-15 | 17:00 | 21:11 | 4:11 | created effort estimation using DAGoPERT template; specified requirements sprint #7; uploaded required documents; updated repository; group meeting
2 | 2022-03-18 | 12:50 | 15:35 | 2:45 | class 2 - meeting to discuss preparations, plan and tasks up to now for sprint #7/#1_2
3 | 2022-03-28 | 16:00 | 19:00 | 3:00 | research; meeting
4 | 2022-03-29 | 13:00 | 15:30 | 2:30 | UI Mockups Version 1 & 2
5 | 2022-03-29 | 18:00 | 21:00 | 3:00 | team meeting (sprint #7) to upload sprint review protocol #7 & create requirements sprint #8
6 | 2022-03-31 | 16:30 | 18:00 | 1:30 | team meeting (sprint #7) to discuss last changes and prepare for meeting with supervisor
7 | 2022-04-04 | 14:15 | 14:40 | 0:25 | update jira tasks
8 | 2022-05-11 | 12:50 | 17:00 | 4:10 | meeting, threading bug
9 | 2022-05-19 | 17:00 | 19:20 | 2:20 | team meeting, update jira tasks
10 | 2022-05-31 | 19:30 | 21:00 | 1:30 | update jira tasks, documentation
11 | 2022-06-01 | 15:00 | 18:00 | 3:00 | multiprocessing research
12 | 2022-06-01 | 19:00 | 19:30 | 0:30 | sprint 11 meeting with supervisor
13 | 2022-06-15 | 12:00 | 13:30 | 1:30 | jira tasks, documentation
14 | 2022-06-24 | 11:40 | 15:35 | 3:55 | jira tasks sprint 13, final documentation
1 | 2022-09-23 | 20:00 | 20:30 | 0:30 | pre-sprint meeting
2 | 2022-09-30 | 19:00 | 19:15 | 0:15 | added backlog tasks
3 | 2022-09-30 | 19:45 | 20:00 | 0:15 | preparing for meeting/github pull
4 | 2022-09-30 | 20:00 | 20:45 | 0:45 | pre-sprint meeting #2
5 | 2022-10-03 | 18:50 | 19:30 | 0:40 | effort estimation
6 | 2022-10-06 | 16:10 | 16:40 | 0:30 | sprint #15 lecturer meeting
7 | 2022-10-27 | 13:30 | 17:15 | 3:45 | choose framework, setup angular, create mockup
8 | 2022-11-08 | 13:00 | 16:00 | 3:00 | website ionic, added tabs, implement skeleton
9 | 2022-11-09 | 15:45 | 16:15 | 0:30 | setting up angular and ionic on home pc
10 | 2022-11-09 | 16:15 | 17:00 | 0:45 | css, filled tabs with dummy data
11 | 2022-11-09 | 18:20 | 18:35 | 0:15 | lecturer meeting sprint 16
12 | 2022-11-22 | 14:00 | 17:15 | 3:15 | mysql setup, pdm setup, struggle
13 | 2022-11-23 | 18:00 | 18:45 | 0:45 | lecturer meeting sprint 17
14 | 2022-12-06 | 15:00 | 18:00 | 3:00 | mqtt in angular
15 | 2022-12-20 | 15:00 | 17:00 | 2:00 | mqtt struggle
16 | 2023-01-14 | 13:00 | 14:00 | 1:00 | group meeting
17 | 2023-01-14 | 14:00 | 17:30 | 3:30 | mqtt connection error
18 | 2023-01-23 | 17:30 | 18:15 | 0:45 | lecturer meeting
19 | 2023-01-29 | 13:30 | 17:00 | 3:30 | paper, project diary
How to use:
for a new entry of time & work start a new line with typing in the proper date and time your started your work
the number of entry (column ‘C’) will appear after starting time is confirmed
type in your ending time in column ‘F’ and after confirming it, your time of work will be calculated and added to the sum
recording what you did with that time, put your work of content in the same line at column ‘H’
“ctrl” + “ü” adds the current date
Thanks for participating!

## time_Jessica
| Jessica Isabella Görög |  |  |  |  | current hours of work - group in total: |  | 145:13
semester #3: | 32:47 | semester #5: |  | 17:00 | developer 1 |  | (group) semester #3: | 169:13
semester #4: | 39:11 | [5 empty] | (group) semester #4: | 221:56
# | date | start | end | duration | content of work
1 | 2021-09-23 | 16:00 | 17:45 | 1:45 | Class 1: Course Startup (discuss project topics to choose, plan to form group together)
2 | 2021-09-23 | 19:00 | 19:50 | 0:50 | chose topic 29 (visitor counter) and formed group via project selection tool
3 | 2021-10-06 | 17:00 | 18:00 | 1:00 | discussed and documentated first ideas of requirements, ORDER questions and collaborations tools
4 | 2021-10-07 | 8:00 | 9:00 | 1:00 | Class 2: presented project supervisor requirements and collaboration tools; got information for project / routines; made appointment for picking up hardware
5 | 2021-10-10 | 19:45 | 20:00 | 0:15 | group meeting ( format of timetable / kanban board / documentation discussed)
6 | 2021-10-11 | 14:20 | 16:00 | 1:40 | group meeting (prepare documentation for self study C)
7 | 2021-10-12 | 16:10 | 16:45 | 0:35 | class 3 - presentation of project diary (chapter 1+2), effort estimation, requirement priorities and sprint planning
8 | 2021-10-14 | 10:30 | 10:45 | 0:15 | Presentation Lab visit (taking measures, photos, brainstorming for positioning of pi+cam)
9 | 2021-11-03 | 9:40 | 11:00 | 1:20 | Team meeting (hardware requirements sprint 1 - reqID3_#1, reqID3_#2)
10 | 2021-11-10 | 17:00 | 17:55 | 0:55 | generated trello tasks and caught up with current status
11 | 2021-11-10 | 18:00 | 18:20 | 0:20 | Suggested names
12 | 2021-11-11 | 16:10 | 16:45 | 0:35 | class 4 - presentation of sprint#1, requirements sprint#2, documentation, PoE malfunction
13 | 2021-11-12 | 11:30 | 12:00 | 0:30 | Team meeting, sprint#2 planing
14 | 24.22.2021 | 2:15 | 4:15 | 2:00 | search for packages/libraries
15 | 24.22.2021 | 11:40 | 11:50 | 0:10 | short meeting
16 | 24.22.2021 | 19:00 | 23:30 | 4:30 | Team meeting, sprint#3 planing & installing packages
17 | 2021-11-25 | 16:10 | 16:45 | 0:35 | class 5 - presentation of sprint#2; requirements sprint#3; Jira; 3D print next steps; PoE status
18 | 2021-11-26 | 2:45 | 5:45 | 3:00 | testing opencv on python environment
19 | 2021-11-27 | 14:00 | 14:45 | 0:45 | meeting
20 | 2021-12-06 | 20:30 | 21:35 | 1:05 | Documentation configure OpenCv
21 | 2021-12-08 | 19:00 | 19:25 | 0:25 | Team meeting, sprint#4 planning
22 | 2021-12-10 | 12:00 | 12:30 | 0:30 | team meeting
23 | 2021-12-15 | 15:05 | 16:07 | 1:02 | team meeting (sprint #4 final)
24 | 2021-12-16 | 16:10 | 16:45 | 0:35 | class 7 - presentation of sprint #4; requirements sprint #5; Jira
25 | 2022-01-02 | 7:09 | 9:04 | 1:55 | educate myself with OpenCv
26 | 2022-01-12 | 18:30 | 19:15 | 0:45 | team meeting (sprint #5 final)
27 | 2022-01-13 | 15:15 | 16:00 | 0:45 | class 8 - presentation of sprint #5; requirements sprint #6; Jira
28 | 2022-01-16 | 10:00 | 13:00 | 3:00 | recording video
29 | 2022-01-20 | 15:15 | 16:00 | 0:45 | class 9 - feedback of final upload; discussion about upcoming semester phase; sharing information to mqtt etc
1 | 2022-03-15 | 19:45 | 21:11 | 1:26 | created effort estimation using DAGoPERT template; specified requirements sprint #7; uploaded required documents; updated repository; group meeting
2 | 2022-03-18 | 12:50 | 13:35 | 0:45 | class 2 - meeting to discuss preparations, plan and tasks up to now for sprint #7/#1_2
3 | 2022-03-25 | 10:15 | 11:30 | 1:15 | research for people detection in different scope
4 | 2022-02-28 | 13:30 | 18:40 | 5:10 | trying to detect multiple objects
5 | 2022-02-28 | 21:45 | 23:10 | 1:25 | trying to detect multiple objects
6 | 2022-03-29 | 20:00 | 21:00 | 1:00 | team meeting (sprint #7) to upload sprint review protocol #7 & create requirements sprint #8
7 | 2022-03-31 | 16:30 | 17:00 | 0:30 | team meeting (sprint #7) to discuss last changes and prepare for meeting with supervisor
8 | 2022-04-19 | 18:30 | 19:30 | 1:00 | team meeting; upload sprint review protocol; specifiying requirements sprint #08
9 | 2022-04-20 | 18:00 | 22:00 | 4:00 | planing further functionality of user interface for local use of raspberry pi
10 | 2022-04-21 | 13:00 | 13:45 | 0:45 | class 4 - presentation of sprint #08; requirements sprint #09
11 | 2022-05-03 | 19:30 | 21:30 | 2:00 | team meeting; upload sprint review protocol; specifiying requirements sprint #09
12 | 2022-05-04 | 11:00 | 14:00 | 3:00 | try to implement automatic start with raspberry pi
13 | 2022-05-05 | 16:00 | 16:45 | 0:45 | class 5 - presentation of sprint #09; requirements sprint #10
14 | 2022-05-17 | 19:00 | 21:05 | 2:05 | team meeting; upload sprint review protocol; specifiying requirements sprint #10
15 | 19:05.2022 | 19:00 | 21:00 | 2:00 | trying tuning auto start
16 | 2022-05-20 | 12:30 | 13:15 | 0:45 | class 6 - presentation of sprint #10; requirements sprint #11
17 | 2022-05-31 | 18:00 | 19:45 | 1:45 | team meeting; upload sprint review protocol; specifiying requirements sprint #11
18 | 2022-06-01 | 19:00 | 19:45 | 0:45 | class 7 - presentation of sprint #11; requirements sprint #12
19 | 2022-06-03 | 18:00 | 21:00 | 3:00 | try fixing bugs
20 | 2022-06-14 | 17:50 | 19:55 | 2:05 | team meeting; upload sprint review protocol; specifiying requirements sprint #12
21 | 2022-06-15 | 16:00 | 16:45 | 0:45 | class 8 - presentation of sprint #12; requirements sprint #13
22 | 2022-06-25 | 17:00 | 20:00 | 3:00 | creating PP
1 | 2022-09-23 | 20:00 | 20:30 | 0:30 | team meeting; discuss topics and tasks for first upload
2 | 2022-09-30 | 10:30 | 12:30 | 2:00 | backlog definitions
3 | 2022-09-30 | 17:55 | 19:50 | 1:55 | prepare DAGoPERT effort estimation; update backlog
4 | 2022-09-30 | 20:00 | 20:40 | 0:40 | team meeting; discuss backlog + effort estimation
5 | 2022-10-03 | 18:00 | 20:00 | 2:00 | start sprint #15; browse alternative person-recognition software
6 | 2022-10-03 | 20:15 | 20:45 | 0:30 | email verkehrt bezüglich project kitchen
7 | 2022-10-23 | 16:25 | 18:20 | 1:55 | discussions 3d case styling, branch work, frame skipping (using single frames instead complete video stream), reseting pi and installing server-image
8 | 2022-10-24 | 17:00 | 17:20 | 0:20 | team meeting; discuss amount of sprint tasks to fulfill; possible date/time for meeting with supervisor; discuss current status
9 | 2022-11-09 | 18:20 | 18:45 | 0:25 | class 4 - presentation sprint #16
10 | 2022-11-23 | 12:00 | 13:00 | 1:00 | prepare sprint review + next sprint
11 | 2022-11-23 | 18:00 | 18:45 | 0:45 | class 5 - presentation sprint #17
12 | 2022-12-07 | 14:30 | 15:15 | 0:45 | class 6 - presentation sprint #18
13 | 2022-12-21 | 17:00 | 17:45 | 0:45 | class 7 - presentation sprint #19
14 | 2023-01-01 | 16:00 | 18:00 | 2:00 | hardware setup (os lite; autostart; source code sync)
15 | 2023-01-23 | 17:30 | 18:00 | 0:30 | class 8 - presentation sprint #20
16 | 2023-01-31 | 21:00 | 22:00 | 1:00 | paper
How to use:
for a new entry of time & work start a new line with typing in the proper date and time your started your work
the number of entry (column ‘C’) will appear after starting time is confirmed
type in your ending time in column ‘F’ and after confirming it, your time of work will be calculated and added to the sum
recording what you did with that time, put your work of content in the same line at column ‘H’
“ctrl” + “ü” adds the current date
Thanks for participating!

## time_Dominic
| Dominic Grabner |  |  |  |  | current hours of work - group in total: |  | 145:13
semester #3: | 31:03 | semester #5: |  | 37:24 | developer 2 |  | (group) semester #3: | 169:13
semester #4: | 36:32 | [5 empty] | (group) semester #4: | 221:56
# | date | start | end | duration | content of work
1 | 2021-09-23 | 16:00 | 17:45 | 1:45 | Class 1: Course Startup (discuss project topics to choose, plan to form group together)
2 | 2021-09-23 | 19:00 | 19:50 | 0:50 | chose topic 29 (visitor counter) and formed group via project selection tool
3 | 2021-10-07 | 8:00 | 9:00 | 1:00 | Class 2: presented project supervisor requirements and collaboration tools; got information for project / routines; made appointment for picking up hardware
4 | 2021-10-10 | 19:45 | 20:00 | 0:15 | group meeting ( format of timetable / kanban board / documentation discussed)
5 | 2021-10-11 | 14:20 | 16:00 | 1:40 | group meeting (prepare documentation for self study C)
6 | 2021-10-12 | 16:10 | 16:45 | 0:35 | class 3 - presentation of project diary (chapter 1+2), effort estimation, requirement priorities and sprint planning
7 | 2021-10-14 | 10:30 | 10:45 | 0:15 | Presentation Lab visit (taking measures, photos, brainstorming for positioning of pi+cam)
8 | 2021-11-03 | 9:40 | 11:00 | 1:20 | Team meeting (hardware requirements sprint 1 - reqID3_#1, reqID3_#2)
9 | 2021-11-03 | 21:00 | 22:00 | 1:00 | extensive research PoE Hat, reinstall PoE hat, Trello Guideline, documentation
10 | 2021-11-10 | 9:00 | 10:30 | 1:30 | Jira account registerd, testing Jira functions, added all sprints in Jira
11 | 2021-11-10 | 17:00 | 17:55 | 0:55 | generated trello tasks and caught up with current status
12 | 2021-11-11 | 16:10 | 16:45 | 0:35 | class 4 - presentation of sprint#1, requirements sprint#2, documentation, PoE malfunction
13 | 2021-11-12 | 11:30 | 12:00 | 0:30 | weekly sprint meeting (assign tasks)
14 | 2021-11-21 | 13:11 | 16:10 | 2:59 | search for 3D Print Model, Trello -> Jira Tasks Export, Google Doc -> Jira Documentation Export
15 | 2021-11-24 | 18:40 | 20:08 | 1:28 | wrote down information from email for 3D print; team meeting (sprint #2 final)
16 | 2021-11-25 | 16:10 | 16:45 | 0:35 | class 5 - presentation of sprint#2; requirements sprint#3; Jira; 3D print next steps; PoE status
17 | 2021-11-26 | 11:30 | 12:00 | 0:30 | weekly sprint meeting - discuss assigned tasks; connected GitHub Repository; arranged date for tutorial
18 | 2021-11-26 | 12:13 | 12:34 | 0:21 | answer email contact for ProjectKitchen
19 | 2021-12-08 | 19:00 | 19:24 | 0:24 | team meeting (sprint #3 final)
20 | 2021-12-09 | 16:10 | 16:30 | 0:20 | class 6 - presentation of sprint#3, requiremnts sprint#3
21 | 2021-12-10 | 12:00 | 12:30 | 0:30 | weekly sprint meeting - discussed and assigned tasks; planned timing for next meeting (real life meeting); discussed plan for final 2 sprints
22 | 2021-12-15 | 15:05 | 16:07 | 1:02 | team meeting (sprint #4 final)
23 | 2021-12-16 | 16:10 | 16:45 | 0:35 | class 7 - presentation of sprint #4; requirements sprint #5; Jira
24 | 2022-01-05 | 9:53 | 11:00 | 1:07 | preperation pycharm, install python interpreter, created project
25 | 2022-01-07 | 2:33 | 3:47 | 1:14 | first tests with webcam capture and recogniztion of persons
26 | 2022-01-07 | 18:19 | 19:00 | 0:41 | find better solution for recognizizion of persons
27 | 2022-01-12 | 18:30 | 19:15 | 0:45 | team meeting (sprint #5 final)
28 | 2022-01-13 | 15:15 | 16:00 | 0:45 | class 8 - presentation of sprint #5; requirements sprint #6; Jira
29 | 2022-01-17 | 17:52 | 20:30 | 2:38 | mqtt preperation and research
30 | 2022-01-18 | 11:30 | 13:44 | 2:14 | mqtt test impementations in python and html/js, tests with websockets client for mqtt with online public broker server
31 | 2022-01-20 | 15:15 | 16:00 | 0:45 | class 9 - feedback of final upload; discussion about upcoming semester phase; sharing information to mqtt etc
1 | 2022-03-15 | 19:45 | 21:11 | 1:26 | created effort estimation using DAGoPERT template; specified requirements sprint #7; uploaded required documents; updated repository; group meeting
2 | 2022-03-18 | 12:50 | 13:35 | 0:45 | class 2 - meeting to discuss preparations, plan and tasks up to now for sprint #7/#1_2
3 | 2022-03-29 | 13:00 | 14:30 | 1:30 | UI Mockups Version 1 & 2
4 | 2022-03-29 | 20:00 | 21:00 | 1:00 | team meeting (sprint #7) to upload sprint review protocol #7 & create requirements sprint #8
5 | 2022-03-31 | 16:30 | 17:00 | 0:30 | team meeting (sprint #7) to discuss last changes and prepare for meeting with supervisor
6 | 2022-05-04 | 12:15 | 12:30 | 0:15 | Meeting
7 | 2022-05-05 | 14:00 | 19:00 | 5:00 | pipenv, .idea folder, autostart on pi, meeting with supervisor, mqtt extracted from main file, setup own pi to test our app, documentation
8 | 2022-05-17 | 19:00 | 21:05 | 2:05 | team meeting; upload sprint review protocol; specifiying requirements sprint #10
9 | 2022-05-20 | 12:30 | 13:15 | 0:45 | class 6 - presentation of sprint #10, requirements sprint #11
10 | 2022-05-31 | 18:00 | 20:17 | 2:17 | team meeting; upload sprint review protocol; specifiying requirements sprint #11
11 | 2022-06-01 | 19:00 | 19:45 | 0:45 | class 7 - presentation of sprint #11, requirements sprint #12
12 | 2022-06-09 | 13:10 | 16:45 | 3:35 | research better alternative for pipenv because its very slowly: poetry, trying to fix errors on install on the console
13 | 2022-06-10 | 16:00 | 17:45 | 1:45 | documentation of poetry
14 | 2022-06-14 | 17:50 | 19:55 | 2:05 | team meeting; upload sprint review protocol; specifiying requirements sprint #12
15 | 2022-06-15 | 9:00 | 14:30 | 5:30 | installing flask and test new library, creating routes for video output of recognition
16 | 2022-06-15 | 16:00 | 16:45 | 0:45 | class 8 - presentation of sprint #12, requirements sprint #13
17 | 2022-06-20 | 11:00 | 12:30 | 1:30 | meeting with stefan und lukas to assign tasks and get an overview of the final video; preperation of the script and test a few settings of obs
18 | 2022-06-21 | 14:30 | 16:00 | 1:30 | guest talk
19 | 2022-06-21 | 16:11 | 18:00 | 1:49 | created video content for final video with stefan and lukas
20 | 2022-06-22 | 12:00 | 13:00 | 1:00 | recording and cutting videos for the final video of semester INNO2
21 | 2022-06-26 | 20:00 | 20:45 | 0:45 | documentation, timetable
1 | 2022-07-02 | 21:45 | 22:30 | 0:45 | order 3d print for the test case for the test pi by a friend
2 | 2022-07-06 | 9:05 | 10:45 | 1:40 | clean the test case with knife part 1
3 | 2022-07-15 | 10:00 | 13:00 | 3:00 | clean the test case with knife part 2, colouring
4 | 2022-09-23 | 20:00 | 20:30 | 0:30 | team meeting; discuss topics and tasks for first upload
5 | 2022-09-30 | 10:30 | 12:30 | 2:00 | backlog definitions
6 | 2022-09-30 | 17:55 | 19:50 | 1:55 | prepare DAGoPERT effort estimation; update backlog
7 | 2022-09-30 | 20:00 | 20:40 | 0:40 | team meeting; discuss backlog + effort estimation
8 | 2022-10-03 | 18:25 | 21:10 | 2:45 | start sprint #15; browse alternative person-recognition software
9 | 2022-10-18 | 14:30 | 15:00 | 0:30 | pickup 3D printed case of raspberry pi
10 | 2022-10-22 | 21:00 | 22:50 | 1:50 | planning tomorrow meeting, searching for algorithms, setup own pi for testing, analyze_image.py with time diff
11 | 2022-10-23 | 16:30 | 19:00 | 2:30 | test analyze_image.py on pi; meeting (split tasks, short programming session); software architecture thoughts
12 | 2022-10-24 | 14:28 | 16:26 | 1:58 | Branch renaming; Mqtt Class: loadConfigFromYamlFile method; logging function, start class diagram
13 | 2022-10-24 | 17:00 | 17:20 | 0:20 | team meeting; discuss amount of sprint tasks to fulfill; possible date/time for meeting with supervisor; discuss current status
14 | 2022-10-24 | 18:45 | 19:40 | 0:55 | pdm: add matplotlib, update HttpStreamer
15 | 2022-11-08 | 15:05 | 16:02 | 0:57 | integrate Recognizer in main and basic threading; delete archived files
16 | 2022-11-09 | 9:50 | 11:40 | 1:50 | docs, flask app in own thread; refactor HttpStreamer Class Part1
17 | 2022-11-09 | 13:20 | 14:10 | 0:50 | refactor HttpStreamer Class Part2
18 | 2022-11-09 | 18:20 | 18:45 | 0:25 | meeting with rohatsch class 4
19 | 21.22.2022 | 12:00 | 14:15 | 2:15 | description backend to frontend img tag flask; refactor HttpStreamer Class Part3; squash commit to main
20 | 2022-11-22 | 15:25 | 16:11 | 0:46 | communication with frontend, bug searching
21 | 2022-11-23 | 10:17 | 11:09 | 0:52 | bug fixing
22 | 2022-11-23 | 18:00 | 18:45 | 0:45 | Meeting with Rohatsch, Sprint Review 17
23 | 2022-11-24 | 11:32 | 13:25 | 1:53 | GIN-Stack local setup on docker for testing purposes
24 | 2022-11-28 | 19:34 | 20:20 | 0:46 | node red setup, mqtt subscriber to debug/influx input
25 | 2022-11-30 | 18:00 | 20:00 | 2:00 | influx setup
26 | 2022-12-06 | 17:40 | 18:32 | 0:52 | Setup database in live system
27 | 2022-12-13 | 15:15 | 17:10 | 1:55 | Vorarbeit, Meeting with Rohatsch, Nacharbeit
How to use:
for a new entry of time & work start a new line with typing in the proper date and time your started your work
the number of entry (column ‘C’) will appear after starting time is confirmed
type in your ending time in column ‘F’ and after confirming it, your time of work will be calculated and added to the sum
recording what you did with that time, put your work of content in the same line at column ‘H’
“ctrl” + “ü” adds the current date
Thanks for participating!

## time_Markus_Volunteer (hidden)
| Markus Duskanich |  |  |  |  | current hours of work - group in total: | 114:14
|  | sum - hours of work: |  | 0:15 | developer 5
# | date | start | end | duration | content of work
1 | 2021-10-14 | 10:30 | 10:45 | 0:15 | Presentation Lab visit (taking measures, photos, brainstorming for positioning of pi+cam)
:D
How to use:
for a new entry of time & work start a new line with typing in the proper date and time your started your work
the number of entry (column ‘C’) will appear after starting time is confirmed
type in your ending time in column ‘F’ and after confirming it, your time of work will be calculated and added to the sum
recording what you did with that time, put your work of content in the same line at column ‘H’
“ctrl” + “ü” adds the current date
Thanks for participating!