## time_Stefan
| Stefan Düx |  |  |  |  | current hours of work - group in total: | 165:00
|  | sum - hours of work: |  | 29:38 | developer 0
# | date | start | end | duration | content of work
1 | 2021-09-23 | 16:00 | 17:45 | 1:45 | Class 1: Course Startup (discuss project topics to choose, plan to form group together)
2 | 2021-09-23 | 19:00 | 19:50 | 0:50 | chose topic 29 (visitor counter) and formed group via project selection tool
3 | 2021-10-06 | 17:00 | 18:00 | 1:00 | discussed and documentated first ideas of requirements, ORDER questions and collaborations tools
4 | 2021-10-07 | 8:00 | 9:00 | 1:00 | Class 2: presented project supervisor requirements and collaboration tools; got information for project / routines; made appointment for picking up hardware
5 | 2021-10-10 | 19:45 | 20:00 | 0:15 | group meeting ( format of timetable / kanban board / documentation discussed)
6 | 2021-10-11 | 14:20 | 16:00 | 1:40 | group meeting (prepare documentation for self study C)
7 | 2021-10-12 | 16:10 | 16:45 | 0:35 | class 3 - presentation of project diary (chapter 1+2), effort estimation, requirement priorities and sprint planning
8 | 2021-10-14 | 10:30 | 10:45 | 0:15 | Presentation Lab visit (taking measures, photos, brainstorming for positioning of pi+cam)
9 | 2021-11-03 | 9:40 | 11:00 | 1:20 | Team meeting (hardware requirements sprint 1 - reqID3_#1, reqID3_#2)
10 | 2021-11-10 | 17:15 | 18:20 | 1:05 | Research which OS to use for the Rasperry Pi. Choose IDE for Python and installed.
11 | 2021-11-11 | 16:10 | 16:45 | 0:35 | class 4 - presentation of sprint#1, requirements sprint#2, documentation, PoE malfunction
12 | 2021-11-24 | 19:00 | 20:10 | 1:10 | sprint meeting (sprint #2 final)
13 | 2021-11-25 | 16:10 | 16:45 | 0:35 | class 5 - presentation of sprint#2; requirements sprint#3; Jira; 3D print next steps; PoE status
14 | 2021-11-25 | 10:00 | 14:30 | 4:30 | Installed opencv on personal pc, set up python virtual environment in pycharm and started testing basic functionality of the program.
15 | 2021-11-26 | 11:30 | 12:00 | 0:30 | weekly sprint meeting - discuss assigned tasks; connected GitHub Repository; arranged date for tutorial
16 | 2021-11-27 | 14:00 | 15:30 | 1:30 | opencv basic setup and use tutorium
17 | 2021-12-08 | 19:00 | 19:24 | 0:24 | team meeting(sprint #3 final)
18 | 2021-12-09 | 16:10 | 16:30 | 0:20 | meeting with lecturer for to close out sprint #3
19 | 2021-12-15 | 15:05 | 16:07 | 1:02 | team meeting (sprint #4 final)
20 | 2021-12-16 | 16:10 | 16:45 | 0:35 | class 7 - presentation of sprint #4; requirements sprint #5; Jira
21 | 2021-12-30 | 17:55 | 19:57 | 2:02 | looking up tutorials for templates and fixes for delivery speed issues
22 | 2022-01-12 | 18:30 | 19:15 | 0:45 | team meeting (sprint #5 final)
23 | 2022-01-13 | 15:15 | 16:00 | 0:45 | class 8 - presentation of sprint #5; requirements sprint #6; Jira
24 | 2022-01-15 | 12:10 | 14:05 | 1:55 | tried out multithreaded python examples and fixed issue with imutils package not loading in pycharm
25 | 2022-01-16 | 10:00 | 13:15 | 3:15 | preparing the script and capturing the video for the last spring with obs
How to use:
for a new entry of time & work start a new line with typing in the proper date and time your started your work
the number of entry (column ‘C’) will appear after starting time is confirmed
type in your ending time in column ‘F’ and after confirming it, your time of work will be calculated and added to the sum
recording what you did with that time, put your work of content in the same line at column ‘H’
“ctrl” + “ü” adds the current date
Thanks for participating!

## time_Jessica
| Jessica Isabella Görög |  |  |  |  | current hours of work - group in total: | 165:00
|  | sum - hours of work: |  | 32:02 | developer 1
# | date | start | end | duration | content of work
1 | 2021-09-23 | 16:00 | 17:45 | 1:45 | Class 1: Course Startup (discuss project topics to choose, plan to form group together)
2 | 2021-09-23 | 19:00 | 19:50 | 0:50 | chose topic 29 (visitor counter) and formed group via project selection tool
3 | 2021-10-06 | 17:00 | 18:00 | 1:00 | discussed and documentated first ideas of requirements, ORDER questions and collaborations tools
4 | 2021-10-07 | 8:00 | 9:00 | 1:00 | Class 2: presented project supervisor requirements and collaboration tools; got information for project / routines; made appointment for picking up hardware
5 | 2021-10-10 | 19:45 | 20:00 | 0:15 | group meeting ( format of timetable / kanban board / documentation discussed)
6 | 2021-10-11 | 14:20 | 16:00 | 1:40 | group meeting (prepare documentation for self study C)
7 | 2021-10-12 | 16:10 | 16:45 | 0:35 | class 3 - presentation of project diary (chapter 1+2), effort estimation, requirement priorities and sprint planning
8 | 2021-10-14 | 10:30 | 10:45 | 0:15 | Presentation Lab visit (taking measures, photos, brainstorming for positioning of pi+cam)
9 | 2021-11-03 | 9:40 | 11:00 | 1:20 | Team meeting (hardware requirements sprint 1 - reqID3_#1, reqID3_#2)
10 | 2021-11-10 | 17:00 | 17:55 | 0:55 | generated trello tasks and caught up with current status
11 | 2021-11-10 | 18:00 | 18:20 | 0:20 | Suggested names
12 | 2021-11-11 | 16:10 | 16:45 | 0:35 | class 4 - presentation of sprint#1, requirements sprint#2, documentation, PoE malfunction
13 | 2021-11-12 | 11:30 | 12:00 | 0:30 | Team meeting, sprint#2 planing
14 | 24.22.2021 | 2:15 | 4:15 | 2:00 | search for packages/libraries
15 | 24.22.2021 | 11:40 | 11:50 | 0:10 | short meeting
16 | 24.22.2021 | 19:00 | 23:30 | 4:30 | Team meeting, sprint#3 planing & installing packages
17 | 2021-11-25 | 16:10 | 16:45 | 0:35 | class 5 - presentation of sprint#2; requirements sprint#3; Jira; 3D print next steps; PoE status
18 | 2021-11-26 | 2:45 | 5:45 | 3:00 | testing opencv on python environment
19 | 2021-11-27 | 14:00 | 14:45 | 0:45 | meeting
20 | 2021-12-06 | 20:30 | 21:35 | 1:05 | Documentation configure OpenCv
21 | 2021-12-08 | 19:00 | 19:25 | 0:25 | Team meeting, sprint#4 planning
22 | 2021-12-10 | 12:00 | 12:30 | 0:30 | team meeting
23 | 2021-12-15 | 15:05 | 16:07 | 1:02 | team meeting (sprint #4 final)
24 | 2021-12-16 | 16:10 | 16:45 | 0:35 | class 7 - presentation of sprint #4; requirements sprint #5; Jira
25 | 2022-01-02 | 7:09 | 9:04 | 1:55 | educate myself with OpenCv
26 | 2022-01-12 | 18:30 | 19:15 | 0:45 | team meeting (sprint #5 final)
27 | 2022-01-13 | 15:15 | 16:00 | 0:45 | class 8 - presentation of sprint #5; requirements sprint #6; Jira
28 | 2022-01-16 | 10:00 | 13:00 | 3:00 | recording video
How to use:
for a new entry of time & work start a new line with typing in the proper date and time your started your work
the number of entry (column ‘C’) will appear after starting time is confirmed
type in your ending time in column ‘F’ and after confirming it, your time of work will be calculated and added to the sum
recording what you did with that time, put your work of content in the same line at column ‘H’
“ctrl” + “ü” adds the current date
Thanks for participating!

## time_Dominic
| Dominic Grabner |  |  |  |  | current hours of work - group in total: | 165:00
|  | sum - hours of work: |  | 30:18 | developer 2
# | date | start | end | duration | content of work
1 | 2021-09-23 | 16:00 | 17:45 | 1:45 | Class 1: Course Startup (discuss project topics to choose, plan to form group together)
2 | 2021-09-23 | 19:00 | 19:50 | 0:50 | chose topic 29 (visitor counter) and formed group via project selection tool
3 | 2021-10-07 | 8:00 | 9:00 | 1:00 | Class 2: presented project supervisor requirements and collaboration tools; got information for project / routines; made appointment for picking up hardware
4 | 2021-10-10 | 19:45 | 20:00 | 0:15 | group meeting ( format of timetable / kanban board / documentation discussed)
5 | 2021-10-11 | 14:20 | 16:00 | 1:40 | group meeting (prepare documentation for self study C)
6 | 2021-10-12 | 16:10 | 16:45 | 0:35 | class 3 - presentation of project diary (chapter 1+2), effort estimation, requirement priorities and sprint planning
7 | 2021-10-14 | 10:30 | 10:45 | 0:15 | Presentation Lab visit (taking measures, photos, brainstorming for positioning of pi+cam)
8 | 2021-11-03 | 9:40 | 11:00 | 1:20 | Team meeting (hardware requirements sprint 1 - reqID3_#1, reqID3_#2)
9 | 2021-11-03 | 21:00 | 22:00 | 1:00 | extensive research PoE Hat, reinstall PoE hat, Trello Guideline, documentation
10 | 2021-11-10 | 9:00 | 10:30 | 1:30 | Jira account registerd, testing Jira functions, added all sprints in Jira
11 | 2021-11-10 | 17:00 | 17:55 | 0:55 | generated trello tasks and caught up with current status
12 | 2021-11-11 | 16:10 | 16:45 | 0:35 | class 4 - presentation of sprint#1, requirements sprint#2, documentation, PoE malfunction
13 | 2021-11-12 | 11:30 | 12:00 | 0:30 | weekly sprint meeting (assign tasks)
14 | 2021-11-21 | 13:11 | 16:10 | 2:59 | search for 3D Print Model, Trello -> Jira Tasks Export, Google Doc -> Jira Documentation Export
15 | 2021-11-24 | 18:40 | 20:08 | 1:28 | wrote down information from email for 3D print; team meeting (sprint #2 final)
16 | 2021-11-25 | 16:10 | 16:45 | 0:35 | class 5 - presentation of sprint#2; requirements sprint#3; Jira; 3D print next steps; PoE status
17 | 2021-11-26 | 11:30 | 12:00 | 0:30 | weekly sprint meeting - discuss assigned tasks; connected GitHub Repository; arranged date for tutorial
18 | 2021-11-26 | 12:13 | 12:34 | 0:21 | answer email contact for ProjectKitchen
19 | 2021-12-08 | 19:00 | 19:24 | 0:24 | team meeting (sprint #3 final)
20 | 2021-12-09 | 16:10 | 16:30 | 0:20 | class 6 - presentation of sprint#3, requiremnts sprint#3
21 | 2021-12-10 | 12:00 | 12:30 | 0:30 | weekly sprint meeting - discussed and assigned tasks; planned timing for next meeting (real life meeting); discussed plan for final 2 sprints
22 | 2021-12-15 | 15:05 | 16:07 | 1:02 | team meeting (sprint #4 final)
23 | 2021-12-16 | 16:10 | 16:45 | 0:35 | class 7 - presentation of sprint #4; requirements sprint #5; Jira
24 | 2022-01-05 | 9:53 | 11:00 | 1:07 | preperation pycharm, install python interpreter, created project
25 | 2022-01-07 | 2:33 | 3:47 | 1:14 | first tests with webcam capture and recogniztion of persons
26 | 2022-01-07 | 18:19 | 19:00 | 0:41 | find better solution for recognizizion of persons
27 | 2022-01-12 | 18:30 | 19:15 | 0:45 | team meeting (sprint #5 final)
28 | 2022-01-13 | 15:15 | 16:00 | 0:45 | class 8 - presentation of sprint #5; requirements sprint #6; Jira
29 | 2022-01-17 | 17:52 | 20:30 | 2:38 | mqtt preperation and research
30 | 2022-01-18 | 11:30 | 13:44 | 2:14 | mqtt test impementations in python and html/js, tests with websockets client for mqtt with online public broker server
How to use:
for a new entry of time & work start a new line with typing in the proper date and time your started your work
the number of entry (column ‘C’) will appear after starting time is confirmed
type in your ending time in column ‘F’ and after confirming it, your time of work will be calculated and added to the sum
recording what you did with that time, put your work of content in the same line at column ‘H’
“ctrl” + “ü” adds the current date
Thanks for participating!

## time_Rebekka
| Rebekka Tscheppen |  |  |  |  | current hours of work - group in total: | 165:00
|  | sum - hours of work: |  | 30:17 | developer 3 |  | 3960:00
# | date | start | end | duration | content of work
1 | 2021-09-23 | 16:00 | 17:45 | 1:45 | Class 1: Course Startup (discuss project topics to choose, plan to form group together)
2 | 2021-09-23 | 19:00 | 19:50 | 0:50 | chose topic 29 (visitor counter) and formed group via project selection tool
3 | 2021-10-06 | 17:00 | 18:00 | 1:00 | discussed and documentated first ideas of requirements, ORDER questions and collaborations tools
4 | 2021-10-07 | 8:00 | 9:00 | 1:00 | Class 2: presented project supervisor requirements and collaboration tools; got information for project / routines; made appointment for picking up hardware
5 | 2021-10-10 | 19:45 | 20:00 | 0:15 | group meeting ( format of timetable / kanban board / documentation discussed)
6 | 2021-10-11 | 14:20 | 16:00 | 1:40 | group meeting (prepare documentation for self study C)
7 | 2021-10-12 | 16:10 | 16:45 | 0:35 | Class 3 - presentation of project diary (chapter 1+2), effort estimation, requirement priorities and sprint planning
8 | 2021-10-14 | 10:30 | 10:45 | 0:15 | Presentation Lab visit (taking measures, photos, brainstorming for positioning of pi+cam)
9 | 2021-11-03 | 9:40 | 11:00 | 1:20 | Team meeting (hardware requirements sprint 1 - reqID3_#1, reqID3_#2)
10 | 2021-11-10 | 17:15 | 18:20 | 1:05 | OS alternatives research + IDE setup (PyCharm)
11 | 2021-11-10 | 18:30 | 19:00 | 0:30 | IDE + Python testing
12 | 2021-11-10 | 19:00 | 20:00 | 1:00 | Team meeting end of sprint1 and sprint 2 planning
13 | 2021-11-11 | 16:10 | 16:45 | 0:35 | class 4 - presentation of sprint#1, requirements sprint#2, documentation, PoE malfunction
14 | 2021-11-12 | 11:30 | 12:00 | 0:30 | team meeting, sprint 2 planning
15 | 2021-11-12 | 12:10 | 12:30 | 0:20 | trello tutorial
16 | 2021-11-12 | 17:45 | 18:00 | 0:15 | sprint2 #12 - create milestones, sprint2 #6 update trello tasks
17 | 2021-11-24 | 14:20 | 14:30 | 0:10 | create Git repository
18 | 2021-11-24 | 19:00 | 20:10 | 1:10 | sprint2 end meeting, sprint 3 planning
19 | 2021-11-24 | 20:10 | 20:30 | 0:20 | jira tutorial
20 | 2021-11-25 | 11:10 | 12:10 | 1:00 | TO29-69 linked github on jira, TO29-68 update jira tasks, try out jira
21 | 2021-11-25 | 16:10 | 16:45 | 0:35 | class 5 - presentation of sprint#2; requirements sprint#3; Jira; 3D print next steps; PoE status
22 | 2021-11-26 | 11:20 | 11:30 | 0:10 | jira sprint 2 complete, spritn 3 start, created issue
23 | 2021-11-26 | 11:30 | 12:02 | 0:32 | sprint 3 meeting
24 | 2021-11-27 | 14:00 | 14:43 | 0:43 | meeting, install opencv, test opencv
25 | 2021-12-08 | 19:00 | 19:25 | 0:25 | sprint 3 end meeting
26 | 2021-12-09 | 16:10 | 16:30 | 0:20 | class 6 - presentation of sprint#3, requiremnts sprint#3
27 | 2021-12-10 | 12:00 | 12:30 | 0:30 | team meeting
28 | 2021-12-10 | 14:30 | 15:00 | 0:30 | communicate with project kitchen
29 | 2021-12-10 | 15:00 | 15:15 | 0:15 | update jira task, confluence notes, pull GitHub repository
30 | 2021-12-15 | 15:05 | 16:07 | 1:02 | team meeting (sprint #4 final)
31 | 2021-12-16 | 16:10 | 16:45 | 0:35 | class 7 - presentation of sprint #4; requirements sprint #5; Jira
32 | 2021-12-18 | 15:31 | 15:50 | 0:19 | update jira tasks
33 | 2021-12-27 | 16:15 | 18:37 | 2:22 | research python bug fixes for more accurate people recognition
34 | 2022-01-01 | 13:55 | 14:42 | 0:47 | update github, setting up ide, test program
35 | 2022-01-12 | 18:30 | 19:15 | 0:45 | team meeting (sprint #5 final)
36 | 2022-01-13 | 15:15 | 16:00 | 0:45 | class 8 - presentation of sprint #5; requirements sprint #6; Jira
37 | 2022-01-15 | 14:00 | 14:19 | 0:19 | update jira tasks, research jira problem with assigning tasks to people
38 | 2022-01-15 | 16:20 | 18:18 | 1:58 | ProjectKitchen email, final documentation, git fetching bug
39 | 2022-01-16 | 12:25 | 14:15 | 1:50 | documentation formatting
How to use:
for a new entry of time & work start a new line with typing in the proper date and time your started your work
the number of entry (column ‘C’) will appear after starting time is confirmed
type in your ending time in column ‘F’ and after confirming it, your time of work will be calculated and added to the sum
recording what you did with that time, put your work of content in the same line at column ‘H’
“ctrl” + “ü” adds the current date
Thanks for participating!

## time_Lukas
| Lukas Varga |  |  |  |  | current hours of work - group in total: | 165:00
|  | sum - hours of work: |  | 42:45 | developer 4
# | date | start | end | duration | content of work
1 | 2021-09-23 | 16:00 | 17:45 | 1:45 | Class 1: Course Startup (discuss project topics to choose, plan to form group together)
2 | 2021-09-23 | 19:00 | 19:50 | 0:50 | chose topic 29 (visitor counter) and formed group via project selection tool
3 | 2021-10-06 | 17:00 | 18:00 | 1:00 | discussed and documentated first ideas of requirements, ORDER questions and collaborations tools
4 | 2021-10-07 | 8:00 | 9:00 | 1:00 | Class 2: presented project supervisor requirements and collaboration tools; got information for project / routines; made appointment for picking up hardware
5 | 2021-10-08 | 19:00 | 21:20 | 2:20 | creating trello board + project schedule (basic data, collaboration tools, member list, management-summary, frame conditions)
6 | 2021-10-10 | 19:45 | 20:00 | 0:15 | group meeting ( format of timetable / kanban board / documentation discussed)
7 | 2021-10-11 | 14:20 | 16:00 | 1:40 | group meeting (prepare documentation for self study C)
8 | 2021-10-11 | 20:00 | 21:50 | 1:50 | formatted current documentation; translated to english; used the most stupid software ever (office 365 online); prepared and uploaded documentation for class 3
9 | 2021-10-12 | 16:10 | 16:45 | 0:35 | class 3 - presentation of project diary (chapter 1+2), effort estimation, requirement priorities and sprint planning
10 | 2021-10-14 | 10:30 | 10:45 | 0:15 | Presentation Lab visit (taking measures, photos, brainstorming for positioning of pi+cam)
11 | 2021-11-03 | 9:40 | 11:00 | 1:20 | Team meeting (hardware requirements sprint 1 - reqID3_#1, reqID3_#2)
12 | 2021-11-09 | 19:30 | 21:20 | 1:50 | create 3D model of Presentation Lab for orientation while planning project, added photos and video from Presentation Lab to Notes
13 | 2021-11-10 | 10:10 | 10:40 | 0:30 | preperation of sprint #2
14 | 2021-11-10 | 19:00 | 20:00 | 1:00 | team meeting (sprint #1 final)
15 | 2021-11-10 | 20:00 | 20:15 | 0:15 | adapted trello tasks (format) and prepared checklist for meeting with supervisor
16 | 2021-11-11 | 16:10 | 16:45 | 0:35 | class 4 - presentation of sprint#1, requirements sprint#2, documentation, PoE malfunction
17 | 2021-11-12 | 11:30 | 12:00 | 0:30 | weekly sprint meeting (assign tasks)
18 | 2021-11-21 | 13:00 | 16:11 | 3:11 | browsed for 3D model blueprints; wrote email to ProjectKitchen & htw office; planed, discussed and switched to Jira Software + Confluence for advanced documentation
19 | 2021-11-23 | 20:13 | 21:01 | 0:48 | adapted tasks; created process types and assigned pictures for better recognition; changed labels
20 | 2021-11-24 | 11:55 | 12:53 | 0:58 | prepared sprint review protocol #2; added jira task for upcoming meeting; added confluence page for sprint #3 requirements
21 | 2021-11-24 | 18:40 | 19:00 | 0:20 | wrote down information from email for 3D print; discussed next step with Dominic
22 | 2021-11-24 | 19:00 | 20:10 | 1:10 | team meeting (sprint #2 final)
23 | 2021-11-24 | 20:10 | 20:30 | 0:20 | explained Jira to Rebekka for upcoming tasks and general handling
24 | 2021-11-25 | 11:10 | 11:41 | 0:31 | assigned Admin rights to Dominic and Rebekka for Jira; added requirement for Sprint#3; discussed Jira settings
25 | 2021-11-25 | 16:10 | 16:45 | 0:35 | class 5 - presentation of sprint#2; requirements sprint#3; Jira; 3D print next steps; PoE status
26 | 2021-11-26 | 6:00 | 6:12 | 0:12 | closing Trello Board; deleting Google Document; customize timetable; set up task for weekly sprint meeting
27 | 2021-11-26 | 11:30 | 12:00 | 0:30 | weekly sprint meeting - discuss assigned tasks; connected GitHub Repository; arranged date for tutorial
28 | 2021-11-26 | 12:13 | 12:34 | 0:21 | answer email contact for ProjectKitchen
29 | 2021-11-27 | 14:00 | 14:45 | 0:45 | tutorium for opencv
30 | 2021-11-28 | 18:35 | 18:46 | 0:11 | edited jira tasks
31 | 2021-12-08 | 14:00 | 15:04 | 1:04 | call with matthias from projectkitchen; adapt tasks; think of next steps for 3D print; preparation sprint meeting (review protocol, tasks, requirements)
32 | 2021-12-08 | 19:00 | 19:24 | 0:24 | team meeting (sprint #3 final)
33 | 2021-12-09 | 16:10 | 16:45 | 0:35 | class 6 - presentation of sprint #3; requirements sprint #4; Jira; ongoing sprints until end of semester #3
34 | 2021-12-10 | 12:00 | 12:30 | 0:30 | weekly sprint meeting - discussed and assigned tasks; planned timing for next meeting (real life meeting); discussed plan for final 2 sprints
35 | 2021-12-10 | 14:30 | 15:00 | 0:30 | answered ProjectKitchen regarding delay of 3D print; saved screenshot of mail; set up regarding task in Jira
36 | 2021-12-15 | 5:35 | 6:00 | 0:25 | adapt settings; prepare for meeting
37 | 2021-12-15 | 6:45 | 7:58 | 1:13 | capture video via opencv
38 | 2021-12-15 | 9:46 | 11:31 | 1:45 | tried version of people recognizing program
39 | 2021-12-15 | 15:05 | 16:07 | 1:02 | team meeting (sprint #4 final)
40 | 2021-12-16 | 16:10 | 16:45 | 0:35 | class 7 - presentation of sprint #4; requirements sprint #5; Jira
41 | 2022-01-12 | 13:19 | 14:58 | 1:39 | adapted code with multithreading
42 | 2022-01-12 | 18:30 | 19:15 | 0:45 | team meeting (sprint #5 final)
43 | 2022-01-13 | 6:00 | 7:42 | 1:42 | bugfix (operation on Windows); bugfix (text output); ~bugfix (speed); updated repository
44 | 2022-01-13 | 15:15 | 16:00 | 0:45 | class 8 - presentation of sprint #5; requirements sprint #6; Jira
45 | 2022-01-15 | 16:20 | 18:19 | 1:59 | answering mail to ProjectKitchen; summarize/prepare documentation for final upload semester #3; tried to synch python project but confronted some bugs
46 | 2022-01-16 | 14:20 | 14:50 | 0:30 | post-editing of project diary
47 | 2022-01-16 | 15:30 | 16:32 | 1:02 | create powerpoint as part of formal requirements for final class semester #3
48 | 2022-01-18 | 8:55 | 9:06 | 0:11 | research grading requirements; email to supervisor to clarify upload of timetable
How to use:
for a new entry of time & work start a new line with typing in the proper date and time your started your work
the number of entry (column ‘C’) will appear after starting time is confirmed
type in your ending time in column ‘F’ and after confirming it, your time of work will be calculated and added to the sum
recording what you did with that time, put your work of content in the same line at column ‘H’
“ctrl” + “ü” adds the current date
Thanks for participating!

## time_Markus_Volunteer (hidden)
| Markus Duskanich |  |  |  |  | current hours of work - group in total: | 122:30
|  | sum - hours of work: |  | 0:15 | developer 5
# | date | start | end | duration | content of work
1 | 2021-10-14 | 10:30 | 10:45 | 0:15 | Presentation Lab visit (taking measures, photos, brainstorming for positioning of pi+cam)
:D
How to use:
for a new entry of time & work start a new line with typing in the proper date and time your started your work
the number of entry (column ‘C’) will appear after starting time is confirmed
type in your ending time in column ‘F’ and after confirming it, your time of work will be calculated and added to the sum
recording what you did with that time, put your work of content in the same line at column ‘H’
“ctrl” + “ü” adds the current date
Thanks for participating!