## Tabelle1
Sprint Review Protocol
Sprint No: |  | #7
Date & Time |  | 29.03.2022, 20:50:00
Group Number |  | 29
Participant 1 |  | Stefan Düx
Participant 2 |  | Jessica Isabella Görög
Participant 3 |  | Dominic Grabner
Participant 4 |  | Rebekka Tscheppen
Participant 5 |  | Lukas Varga
Mentor |  | Lukas Rohatsch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
#7reqID2_01 | browse software alternatives | 6 | 4 | -2
#7reqID2_02 | discuss supervisor requirements | 0.5 | 0.5 | 0
#7reqID2_03 | adapt software (recognition) | 8 | 10 | 2
#7reqID4_04 | Jira Tasks | 1 | 0.75 | -0.25
#7reqID4_05 | GitHub repository update | 0.5 | 0.25 | -0.25
#7reqID4_06 | Mail ProjectKitchen | 0.5 | 0.25 | -0.25
#7reqID4_07 | Mail Supervisor | 0.5 | 0.25 | -0.25
#7reqID4_08 | choose mockup software tool | 1.5 | 0.5 | -1
#7reqID4_09 | create 2 mockups | 4 | 2.5 | -1.5
#7reqID4_10 | discuss DAGoPERT + Tshirt sizing | 0.5 | 0.25 | -0.25
10 |  |  |  | -3.75 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol