## Tabelle1
Sprint Review Protocol
Sprint No: |  | #5
Date & Time |  | 12.01.2022, 18:30:00
Group Number |  | 29
Participant 1 |  | Stefan Düx
Participant 2 |  | Jessica Isabella Görög
Participant 3 |  | Dominic Grabner
Participant 4 |  | Rebekka Tscheppen
Participant 5 |  | Lukas Varga
Mentor |  | Lukas Rohatsch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | bug (speed) | 3 | 1.5 | -1.5 | 1
2 | bug (recognition) | 3 | 2.5 | -0.5 | 1
3 | improve (recognition) | 2 | 2.5 | 0.5 | 1
4 | adapt display of text | 1 | 0.75 | -0.25 | 1
5 | adapt source code | 2 | 1.75 | -0.25 | 1
6 | update Jira | 0.5 | 0.5 | 0 | 1
7 | update GitHub | 0.5 | 0.5 | 0 | 1
8 | add python | 0.5 | 1 | 0.5 | 1
9 |  |  |  | 0 |  | 0
10 | reminder ProjectKitchen | 0.5 | 0.5 | 0 | 1
10 |  |  |  | -1.5 | 9 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol