## Tabelle1
Sprint Review Protocol
Sprint No: |  | #1
Date & Time |  | 10.11.2021, 19:30:00
Group Number |  | 29
Participant 1 |  | Stefan Düx
Participant 2 |  | Jessica Isabella Görög
Participant 3 |  | Dominic Grabner
Participant 4 |  | Rebekka Tscheppen
Participant 5 |  | Lukas Varga
Mentor |  | Lukas Rohatsch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
2_1 | check for alternative OS | 2 | 1 | -1 | 1
2_2 | install packages | 1.5 | 1.3 | -0.2 | 1
2_3 | try camera livestream | 1 | 0.75 | -0.25 | 1
2_4 | choose IDE | 2 | 1 | -1 | 1
3_1 | check hardware quality | 1 | 1.3 | 0.3 | 1 |  | PoE malfunction
3_2 | test hardware functionality | 1 | 1.3 | 0.3 | 1
4_1 | create trello tasks | 1 | 1.25 | 0.25 | 1
4_2 | GitHub + Domain name | 0.5 | 0.25 | -0.25 | 1
4_3 | adapt Semester Roadmap | 0.5 | 0.25 | -0.25 | 1
4_4 | add 3D model PresentationLab | 1.5 | 1.5 | 0 | 1
4_5 | photo documentation | 0.5 | 1 | 0 | 1
0
12 |  |  |  | -2.1 | 10 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol