## Tabelle1
Sprint Review Protocol
Sprint No:
Date & Time
Group Number
Participant 1
Participant 2
Participant 3
Participant 4
Participant 5
Mentor
List the Ids of the Requirements which are subject to the review
req ID | short description [opt] | Estimate [h] | Real Effort [h] | Delta [h] | Passed | failed | remarks
#1 | swap PoE (malfunction) | 0.5 | 0.5 | 0
#2 | install chosen IDE | 0.5 | 0.5 | 0
#3 | search libraries / packages | 3.5 | 3 | -0.5
#4 | install new packages | 1.5 | 4 | 2.5
#5 | test new packages | 2 | 0 | -2 |  | 1
#6 | update trello tasks | 0.5 | 0.5 | 0
#7 | create GitHub Rep | 0.5 | 0.5 | 0
#8 | upload elements to Rep | 1 | 0.75 | -0.25
#9 | determine constant meeting | 0.25 | 0.25 | 0
#10 | embed Jira | 2 | 3.5 | 1.5
#11 | 3D model planning | 2 | 2.5 | 0.5
#12 | create Milestones | 0.5 | 0.25 | -0.25
12 |  |  |  | 1.25 | 0 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol