## Tabelle1
Sprint Review Protocol
Sprint No: |  | #3
Date & Time |  | 08.12.2021, 19:15:00
Group Number |  | 29
Participant 1 |  | Stefan Düx
Participant 2 |  | Jessica Isabella Görög
Participant 3 |  | Dominic Grabner
Participant 4 |  | Rebekka Tscheppen
Participant 5 |  | Lukas Varga
Mentor |  | Lukas Rohatsch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | clarify status PoE | 0.25 | 0.25 | 0 | 1
2 | adapt missing libraries / packages | 1.5 | 1 | -0.5 | 1
3 | test adapted libraries / packages | 2 | 2 | 0 | 1
4 | tutorium opencv | 1 | 0.75 | -0.25 | 1
5 | test / use new packages in team | 2.5 | 0 | -2.5 |  | 0
6 | generate test video (dummy data) | 1 | 0.5 | -0.5 | 1
7 | print 3D hardware case | 2.5 | 0 | -2.5 |  | 0
8 | update Jira tasks | 1 | 2 | 1 | 1
9 | connect GitHub repository | 0.5 | 0.5 | 0 | 1
10 | communication ProjectKitchen | 0.5 | 1 | 0.5 | 1
11 | plan 3d print process | 1 | 0.5 | -0.5 | 1
11 |  |  |  | -5.25 | 9 | 2
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol