## Tabelle1
Sprint Review Protocol
Sprint No: |  | 18
Date & Time |  | 06.12.2022
Group Number |  | 29
Participant 1 |  | Stefan Düx
Participant 2 |  | Jessica Isabella Görög
Participant 3 |  | Dominic Grabner
Participant 4 |  | Rebekka Tscheppen
Participant 5 |  | Lukas Varga
Mentor |  | Lukas Rohatsch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
TO29-320 | Execute and test (live demo) existing project on Raspberry Pi and test functionality | 3 | 1 | -2
TO29-323 | Setup autostart | 4 | 2 | -2
TO29-324 | Build Raspberry Pi hardware setup | 2 | 0 | -2
TO29-389 | connect database | 6 | 1 | -5
TO29-392 | implement views | 3 | 1 | -2
TO29-394 | implementing functionality | 3 | 2 | -1
TO29-333 | Setup datatable columns | 6 | 3 | -3
TO29-334 | Implement connection in Python script | 0 | 0 | 0
TO29-335 | Synch new implementation to Raspberry Pi | 2 | 1.5 | -0.5
0 |  |  |  | -17.5 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol