## Tabelle1
Sprint Review Protocol
Sprint No: |  | 19
Date & Time |  | 20.12.2022
Group Number |  | 29
Participant 1 |  | Stefan Düx
Participant 2 |  | Jessica Isabella Görög
Participant 3 |  | Dominic Grabner
Participant 4 |  | Rebekka Tscheppen
Participant 5 |  | Lukas Varga
Mentor |  | Lukas Rohatsch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
TO29-323 | Execute and test (live demo) existing project on Raspberry Pi and test functionality | 4 | 2 | -2
TO29-330 | Build Raspberry Pi hardware setup | 4 | 0 | -4
TO29-389 | connect database | 6 | 2 | -4
TO29-392 | implement views | 6 | 1 | -5
TO29-394 | implementing functionality | 6 | 1 | -5
TO29-336 | Testing | 6 | 1 | -5
TO29-411 | Adapt influxDB data handling (other results from time to time) | 4 | 0.5 | -3.5
TO29-412 | Set influxdb datastream to public access | 2 | 0.5 | -1.5
8 |  |  |  | -30 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol