## Tabelle1
Sprint Review Protocol
Sprint No: |  | 17
Date & Time |  | 22.11.2022
Group Number |  | 29
Participant 1 |  | Stefan Düx
Participant 2 |  | Jessica Isabella Görög
Participant 3 |  | Dominic Grabner
Participant 4 |  | Rebekka Tscheppen
Participant 5 |  | Lukas Varga
Mentor |  | Lukas Rohatsch
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
TO29-402 | implement flask on python script (sending stream picture to FE) | 4 | 3 | -1
TO29-371 | create new demo video to test functionality | 2 | 0.5 | -1.5
TO29-318 | Testing of performance and functionality on Windows system | 4 | 1 | -3
TO29-403 | Get bill from HTW for 3d print | 1 | 0.5 | -0.5
TO29-320 | Install all necessary packages / DB | 6 | 2.5 | -3.5
TO29-323 | Execute and test (live demo) existing project on Raspberry Pi and test functionality | 4 | 0 | -4
TO29-324 | Setup autostart | 4 | 0 | -4
TO29-389 | connect database | 6 | 2.5 | -3.5
TO29-392 | implement views | 6 | 1 | -5
TO29-333 | Setup datatable columns | 6 | 0 | -6
TO29-334 | Implement connection in Python script | 4 | 0 | -4
TO29-335 | Synch new implementation to Raspberry Pi | 2 | 0 | -2
12 |  |  |  | -38 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol